交通建設ＢＯＴ案政府對民間造成之風險分析

-以中正捷運線為例-

研究生：鍾啟椿                 指導教授：馮正民

國立交通大學交通運輸研究所

摘    要

為因應日益複雜且繁重的旅次需求，重大交通建設的推動勢在必行，而重大交通建設往往具有投資成本高、建設期長等特性，長期以往將對政府財政造成相當大的負擔，因此，將民間資金力量引入重大交通建設實為當務之急。然而在民營化過程中可能遭遇到的種種風險卻是造成民間投資者卻步的主因。以往的研究並未能提供相關風險的衡量模式，因此，如何找出民間參與BOT計劃案時可能遭遇的風險，並進一步衡量分析來自於政府方面的風險大小，將有助於政府交通建設單位和民間專案特許公司契約談判之參考及擬訂避險策略之依據，此即為本研究所欲探討的課題。

本研究以風險管理為架構，模糊理論為基礎，結合總損失分配法，依特許年限包含建設期有無構建兩套風險衡量模式，再分別探討分析BOT案例中因土地取得延遲和政府政策改變造成運量減少導致之投資成本增加風險及營運收入減少風險。最後以中正捷運線為例，衡量各風險情境下的風險總值並進行敏感度分析，再配合獎參條例等相關條文的規定，找出適當之避險方法與風險管理策略。

就風險和營建效率觀點而言，特許年限自建設期起之模式較營運期起為佳。民間專案特許公司在面對BOT計劃案產生之風險時可向政府方面取得適當保證或採取投保、融資等避險策略，而政府單位也應增修相關之法律條文並提供運量不足補貼或融資優惠等措施以增加民間投資的誘因，俾利於重大交通建設的推行。

Study on Risks Caused by Government to Private Investor

in BOT Transportation Project

－A Case Study of CKS Airport Link Rapid Transit System－

Student: Chi-Chun Chung                      Advisor: Dr.Cheng-Min Feng

Institute of Traffic and Transportation

National Chiao Tung University

ABSTRACT

In order to accommodate and satisfy the increasingly transportation needs of today and tomorrow, tremendous amount of capital has been invested in long-term transportation infrastructure projects, which results in huge fiscal strain on the government. Thus, it is prudent for the government to encourage private investments in the infrastructure projects. The risks , however, associated with projects are inherently high, as the changing social and political environment may lead to policy changes unfavourable to investors.

The past research has not yet provided a satisfactory framework for evaluation of risks faced by private investors in these "build-operate-transfer（BOT）" projects. Nor is there a proper framework to evaluate risks over uncertainty on public policy in the long-run. Therefore, the purpose of this research to propose a framework to evaluate risks faced by private investors to help the negotiation between public and  private sectors and prepare the risk management strategies.

The proposed evaluation framework is based on risk management, and employs fuzzy theory and aggregate loss distribution method. This framework provides two evaluation models depending on whether the concession period includes the design and construction of the project or not. This study analyzes the risks caused by government on two sides：the delay of land acquisition and decrease in operating revenues due to transportation policy change. A case study on CKS Airport Link Rapid Transit System is conducted to determine the above risks and risk sensitivities.

Taking into account of risks and operating efficiency, the BOT project is more favorable if the design and construction of the project are included in the contract. Private Investors, to decrease exposure to political uncertainty, may either 1) request from the government guarantees of certain support/terms to prevent financial loss from happening, or 2) explore re-insurance alternatives or financial options such as re-financing, etc. Similarly, the involved government body can and should provide and create more favourable investment conditions through changes to the existing regulations or the enactment of new regulations, such as government subsidy or preferential financial loans, etc.

誌謝

連日來的焚膏繼晷，論文終告完成，在五更初啼之際看到多日來的心血結晶付梓，首先浮現腦明的便是恩師馮教授正民於這段時間裡對學生不厭其煩的悉心指導。從思考方向的啟迪、研究架構的開導、模式構建的斧正，乃至於論文寫作的要領，一步一步引領著學生從無到有完成了人生中第一本著作。而老師待人處世的態度及泱泱學者風範，典範夙昔深植學生心中。僅以卷首致以深摯敬意聊表感佩之心。

論文口試期間，承蒙交通部運輸研究所張所長有恆與台灣大學土木工程所張教授學孔於公務繁忙之際撥冗細審，對本論文提出精闢入裡之見解與意見，使得本研究得以精益求精，於此，本人也銘感五內。

論文寫作期間，除了馮老師的悉心指導外，藍武王老師及黃台生老師對學生論文初稿的細心指教，也使學生獲益良多。此外，在研究所修業期間，承蒙曾國雄老師、陳武正老師、張家祝老師、王傳芳老師、汪進財老師、黃承傳老師、陳椿亮老師、張新立老師、吳水威老師等的用心指導，使得學生能初窺學術殿堂之奧妙。而在論文寫作過程中，不時有遭遇挫折之處，幸賴林楨家學長、陳天賜學長及陳郁文學長不時的予以啟發協助。而在資料收集期間也特別要感謝劉至得學長、張蓓琪學姊、劉淑娟學姊及省住都局捷運工程處陳課長清全等人的鼎力相助，本論文方得順利完成，在此僅獻上本人深深的謝意。

遨遊於浩瀚學海，難免會有徬徨之際，感謝靶子、心琪、廣堂、大毛、大牛、小莊、丞邦、弦霖等同窗好友讓我的研究生活多采多姿。特別要感謝皓平，在這將近一年的期間裡陪伴著我，在我面臨壓力之際，給我無限的鼓勵和支持，度過一次又一次的難關。

然而，最要感謝的當然是我的父母親，感謝他們給了我一個溫暖的家，是他們的無悔的關愛讓我無後顧之憂的馳騁於人生的旅途上，這一切的一切都是他們所賜予我的，真心的感謝我親愛的父母親。

僅以此論文獻給我生命中的親人朋友，謝謝你們！

鍾啟椿 謹誌於

交通大學交通運輸研究所

丁丑年夏

目錄

中文摘要……………………..…………………….……………………..i

英文摘要…………………………………………………………………ii

誌謝…………..………………………………………………………….iii

目錄……….…..…………………………………………………………iv

表目錄………..……….…………..……………………………………viii

圖目錄…….……..……………………………………………………..xi

第一章 緒論………..…...…………….………………………1

1.1研究動機………………………………………………………….1

1.2研究目的………………………………………………………….2

1.3研究範疇………………………………………………………….3

1.3.1內容方面……………………………………………………3

1.3.2時間方面……………………………………………………4

1.4研究流程………………………………………………………….5

1.5研究內容與方法………………………………………………….6

1.5.1研究內容……………………………………………………6

1.5.2研究方法……………………………………………………6

第二章 文獻回顧與探討.….…………...………..………….9

2.1民間參與交通建設模式……..….….………………………..…..9

BOT計畫的理論基礎….……….….…………….……….9

交通建設民營化之形式與種類...….....…………………11

BOT計劃之風險特性與內容….……..…….……………12

國內外BOT案例之介紹….……………..……………...16

小結…………………..….…………………………….…20

2.2風險管理….…….………………………………………………20

2.1風險管理的架構……..…………………………………..20

2.2.2風險定義….………....…..……………………………….21

2.2.3小結…………....……………..………………………….22

2.3風險衡量的方法…………....……..…………………………….22

2.3.1傳統統計法………….……………………………….……22

2.3.2百分位數法………………………………………..………24

2.3.3迴歸分析和模糊迴歸………………………..……………26

2.3.4總損失分配法……………………………………………..27

2.3.5小結……………………………………………..…………28

2.4模糊理論的應用…..………………………………………….…29

4.1常用的模糊歸屬函數…….…………………………….…29

2.4.2 模糊語意風險程度的構建.………………………………32

2.5小結…….……………………………………………………..…34

第三章 理論模式構建……….………...…………………...35

- 3.1風險確認……………………..………………………………….35

- 3.1.1風險架構……………………………….…………………35

- 3.1.2各階段風險內容………….……………..……………..…37

- 3.1.3小結……..…………….……..……………………………39

- 3.2理論架構與模式分析……………………………………………40

- 3.2.1風險衡量之理論架構…….…………………….…………40

- 3.2.2模式內容…………………….………………………….…42

- 3.2.3模式假設.……………………………………………….…42

- 3.3語意風險程度隸屬度的建立……………………………………42

- 3.4風險可能性分布與風險機率函數………………………………48

3.4.1土地取得延遲可能性分布……….……………….………50

- 3.4.2運量高估可能性分布…………….….……………………54

- 3.5風險函數構建….….……………………….……………………60

- 3.5.1投資成本增加風險…………….………………………….61

- 5.2營運收入減少風險……………….……………………….62

- 第四章 問卷設計與資料分析….………..….………………70

4.1案例之基本資料分析…………………………………………...70

4.1.1路線規劃……………..…………………….…………….71

4.1.2營運規劃……………..…………………….…………….74

4.1.3財務規劃……………..…………………….…………….76

4.1.4相關風險之確認………..…………………..……………79

4.2問卷設計….………………………..………………………..….81

4.2.1調查對象與調查情形…..………………………………..81

4.2.2問卷內容………………………………………….………82

4.3資料分析…………………………………………………………83

4.3.1土地取得每次延遲年數…………………………………..83

4.3.2土地取得延遲次數………………………………..………85

4.3.3政府政策改變導致運量減少……………………..………86

4.4語意風險程度隸屬函數之建立與風險可能性分布……………89

4.4.1土地取得每次延遲年數…………………….……………89

4.4.2土地取得延遲次數…………………….…………………92

4.4.3土地取得總延遲年數的機率分布………………….……95

- 4.4.4政府政策改變致使運量減少………………….…………97

- 第五章 中正捷運線之風險衡量與管理…………..………103

- 5.1風險損失值估計…………………………………..……………103

5.1.1投資成本…….…………………………………………..103

5.1.2營運成本……..………………………………………….108

5.2風險總值之衡量…………………………….………………….109

5.2.1投資成本增加風險………………………………………110

5.2.2營運收入減少風險………………………………………110

5.2.3風險總值………………………………………………...113

5.2.4小結……………………………………………..……….121

3敏感度分析……………………………….……………………122

5.3.1敏感度分析-特許年限自營運期始………………..……123

5.3.2敏感度分析-特許年限自營運期始………………..……129

5.3.3小結……………………………..………………….……135

5.4風險管理的方法……………………………………….………137

第六章 結論與建議…………………………………………142

1結論……………….……………………………………………142

6.2建議……………….……………………………………………144

參考文獻……………….…………………….………………..………146

附錄：問卷設計……………………….…….………………………..149

簡歷……………………………………………………………………157

表目錄

表2.1重大建設工程預算執行情形……….…….…..……………………12

表2.2風險來源…………………………….…….…..……………………13

表2.3相關風險與解決辦法……………….….……..……………………15

表2.4各國ＢＯＴ案例之比較………………..……..……………………17

表3.1ＢＯＴ專案之可能風險………………..……..……………………38

表3.2政府造成之風險……………………..………..……………………39

表3.3語意風險程度統計表……………..…………..……………………46

表3.4語意風險程度選擇統計表…………..………..……………………48

表3.5土地取得延遲總年數機率分布………..……..……………………51

表3.6語意尺度統計表………………………..……..……………………51

表3.7延遲年數可能性分布…………………..…..………………………52

表3.8延遲年數機率分布型態………………..…..………………………52

表3.9延遲次數可能性分布………………………………………………52

表3.10土地取得總延遲年數機率分布…………….....…………………54

表3.11運量預測表…………………………………....…………..………58

表3.12語意尺度統計表…………………………….….…………………59

表3.13運量估計錯誤之可能性分布……………….…….………………59

表3.14運量估計錯誤之機率分布型態…………..………………………59

表3.15預期運量損失表……………………………..……………………60

表3.16特許年限自營運期始風險總值函數……..……..…..……………65

表3.16特許年限自建設期始風險總值函數….………….………………68

表4.1私有用地取得擬請配合事項表………….…….……..……………72

表4.2規畫路線權屬分析表………………….……...……………………73

表4.3各規劃年度運量需求………………….……...……………………74

表4.4每年旅次預測運量…………………….…….…..…………………75

表4.5各規劃年度之輸送作業設定條件….………….…..………………76

表4.6建造成本估計………………….……………….……..……………77

表4.7預期營運票價收入表…………….………….…………..…………78

表4.8問卷調查對象與情形…………………………...…………….……81

表4.9土地取得每次延遲年數語意風險程度統計表……..………..……83

表4.10土地取得每次延遲年數語意尺度選擇統計表……….…….……85

表4.11土地取得延遲次數語意風險程度統計表………..………………85

表4.12土地取得延遲次數語意尺度選擇統計表……….….……………86

表4.13運量不足語意風險程度統計表………………….….……………86

表4.14政策一運量不足語意尺度選擇統計表…………….….…………88

表4.15政策二運量不足語意尺度選擇統計表………….….……………88

表4.16政策三運量不足語意尺度選擇統計表…………….….…………88

表4.17政策發生可能性統計表……………………………..……………89

表4.18延遲年數相對於各語意程度的隸屬函數值……….….…………91

表4.19延遲年數的可能性分布及機率分布型態………….….…………92

表4.20延遲次數相對於各語意風險程度的隸屬函數值….….…………94

表4.21延遲次數的可能性分布及機率分布型態………….….…………94

表4.22土地取得每次延遲年數之機率分布……………….…….………96

表4.23土地取得總延遲年數之機率分布………………….…….………96

表4.24減少運量相對於各語意風險程度的隸屬函數值….………...…100

表4.25政策一減少運量之可能性分布及機率分布……….………...…100

表4.26政策一運量損失表……………...………………….……………101

表4.27政策二減少運量之可能性分布及機率分布……....……………101

表4.28政策二運量損失表………………...……………….……………101

表4.29政策三減少運量之可能性分布及機率分布………....…………102

表4.30政策三運量損失表……………...………………….……………102

表5.1各設備之設備價值、殘值、使用年限及折舊率…….…………….104

表5.2電力設備折舊情形………………….……………….……………105

表5.3號誌系統折舊情形…………………………….…….……………106

表5.4電聯車折舊情形…………………………….……….……………106

表5.5自動收費系統折舊情形…………….……………….……………107

表5.6營運成本表……………………………….………….……………109

表5.7營運年間票價表…………………….……………….……………111

表5.8營運年間全程旅次預測運量……….……………….……………111

表5.9不同政策對運量之影響…………….……………….……………112

表5.10特許年限自營運期始之風險值表………………………………116

表5.11特許年限自營運期始之風險總值表………………....…………116

表5.12特許年限自建設期始之風險值表…….……..…….……………120

表5.13特許年限自建設期始之風險總值表………...…….……………120

表5.14特許年限自營運期始之折現率敏感度分析表…….…...………124

表5.15特許年限自營運期始之貸款利率敏感度分析表....……………124

表5.16特許年限自營運期始之特許年限敏感度分析表…...…………125

表5.17特許年限自營運期始之土地取得總延遲年數敏感度分析表....125

表5.18特許年限自營運期始之風險事件及發生年敏感度分析表……127

表5.19特許年限自建設期始之折現率敏感度分析表…………..…..…129

表5.20特許年限自建設期始之交通用低租金敏感度分析表…...….…130

表5.21特許年限自建設期始之貸款利率敏感度分析表……...…….…130

表5.22特許年限自建設期始之特許年限敏感度分析表…...……….…131

表5.23特許年限自建設期始之土地取得總延遲年數敏感度分析表....131

表5.24特許年限自建設期始之風險事件及發生年敏感度分析表....…133

圖目錄

圖1.1研究內容界定圖.………………………….…………………………3

圖1.2研究流程圖………………….…………….…………………………5

圖2.1營建階段風險關係圖.……….………………..……………………13

圖2.2Ａ－函數…………….……….……………..………………………30

圖2.3Ｓ－函數及Ｚ－函數……….…...…………………………………31

圖2.4ＰＩ函數…………………….………..……………………………31

圖2.5模糊語意風險程度圖……….………..……………………………32

圖2.6模糊真值圖………………….……………...………………………33

圖3.1風險關係架構圖…………….……...………………………………36

圖3.2ＢＯＴ專案計劃之主要執行階段及內容……...….………………38

圖3.3研究架構流程圖…….…………..………………….………………41

圖3.4三角模糊集合………….………..………………….………………44

圖3.5最小語意之圖形與函數………...………………….………………45

圖3.6最大語意之圖形與函數….……………..………….………………45圖3.7五等分之語意隸屬函數分布圖……………...…….………………45

圖3.8模糊三角函數語意風險程度分布圖…...………….………………48

圖3.9影響運量因素範疇……………………...………….………………56

圖3.10運量估計和ｔ期運量不足風險示意圖…….…….………………57

圖3.11運量估計錯誤語意風險程度隸屬函數圖….…….………………59

圖4.1延遲年數語意風險程度函數圖……………………..…..…………91

圖4.2延遲次數語意風險程度函數圖……………………....……………94

圖4.3運量不足語意風險程度函數圖………………...….………………99

圖5.1特許年限自營運期始之敏感度分析蛛網圖……….…………….126

圖5.2特許年限自營運期始之風險事件敏感度分析圖….………….…128

圖5.3特許年限自建設期始之敏感度分析蛛網圖……….…………….132

圖5.4特許年限自建設期始之風險事件敏感度分析圖….………….…134