Title of Thesis:										       Total Pages: 131

Risk Management for National Traffic Information Management Center using Public-Private-Partnership Models

Keywords：PPP, risk treatment, hierarchy analysis and fuzzy theory

Name of Institute:

Graduate Institute of Transportation Science, Tamkang University

# Graduate Date: June 2004				Degree Conferred: Master Degree

# Name of Student: Chung-Jung Wu		Advisor: Dr. Chi-Chung Tao

吳   忠   榮				陶   治   中     博士

Abstract:

The purpose of this research is to analyze risk factors that influence different alternatives for National Traffic Information Management Center (NTIMC) using Public-Private-Partnership (PPP) models.  The implementation of NTIMC will be based on the study results and achieve operational sustainability in the future.

Referring to risk management theories, this research process can be divided into three parts: risk identification, risk analysis and risk process.  First, some PPP projects relating to Traffic Information Management Center worldwide are reviewed to clarified characteristics and items of risk management of PPP.  With identification of risk responsibilities and capability of risk control, the Analytical Hierarchy Process combining fuzzy theory will be used as a qualitative approach to estimate the risk loss and risk probabilities. Capability of risk control, risk allocation, risk strategic checklist and matrix are used in risk process to derive “investment planning” and “contract negotiation” as two- step operational mechanism of risk management.

NTIMC is chosen as the empirical study by using a hierarchy framework including 6 risk objectives (politics, law, construction, finance, management, information) and 18 risk criteria. It is found that weight of financial risk is highest and weight of law risk is lowest for each alternative. Operating income risk is high in every project while governmental operating project that fails to get promise of continuously operating risk is very low and the fact that is equal to priority knowledge.  The degree of revenue risk is also high for each alternative.  The 6th alternative (BOO) reveals a long-term steady contract relationship. The risk of some BOO’s items is lower than that of BOT. It is also shown that information risk is not significant among all alternatives, while the weight of reliability is the highest one.