CHAPTER 1 INTRODUCTION

The developing of aviation industry, a strategic industry with advance technology, is the key point for the whole industry.  In order to be globally competitive, many countries are eager to find out innovative ways to improve the development efficiency.  The engine maintenance schedule is one of the concerned issues.

If engine maintenance schedule does not take into consideration during early analysis and planning phase, not only increased risk on the operation, cost efficiency are also greatly sacrificed.  In order to establish an advantageous operation environment for engine maintenance schedule and in turn enhance the competitive edge of the company in the worldwide market, company must have an efficient engine maintenance schedule.  In this research, we discuss the engine disassembly process for a company, which is one of the tasks of engine maintenance process.

The operations in the engine maintenance company can be divided into four stages: Gate 0, Gate 1, Gate 2 and Gate 3.  At Gate 0, document including engine work scope and work order must be prepared.  At Gate 1, the engine is disassembled and prepared for maintenance.  At Gate 2, the disassembled parts are maintained in the company.  Some of them will be shipped to outside vender if necessary.  At Gate 3, all parts of engine are gathered and assembled.

The major five modules for an engine include FAN module, HPC module, HPT module, LPT module, and AGB module, as shown in Fig. 1.1.  HPC module includes CRF, rotor and stator part.  HPT module includes T2N, rotor and stator part.  LPT module includes rotor and stator part.  The combination of HPC and HPT module is called the Core module.

LPT

AGB

FAN

HPC

HPT

Core module

Fig. 1.1 Aircraft engine

The research objectives of this thesis are as follows.  We schedule the engine disassembly process.  The suitable solution not only can minimize the disassembly time for engines, also can minimize worker demand for system.

The research scope of this thesis are as follows.  We discuss the engine disassembly processes for a company.  There are three kinds of disassembly levels, namely, minimum, performance and overhaul.  Minimum means the engine disassembly for exterior inspection.  Performance means some module of the engine should be disassembled completely.  Overhaul means every module of the engine should be disassembled completely.  In this research all of the disassembly engines are in overhaul situation.

The organization of this thesis is as follows.  Chapter 2 reviews the literature of related research work.  Chapter 3 describes the current status of the engine disassembly process for a specific company in Taiwan (called company A in this thesis).  Chapter 4 presents a mixed integer programming (MIP) model for engine disassembly process.  Chapter 5 illustrates the solutions for the engine disassembly process case described in chapter 3.  Finally, the conclusions and the future research suggestions are discussed in chapter 6.

CHAPTER 2 LITERATURE REVIEW

We consider the engine disassembly process, which could be viewed as a job shop scheduling problem.  Job shop scheduling is a NP-hard problem (Lenstra et al. [23]; Gray and Johnson [24]) that means the probability of finding an efficient procedure for optimal solution is low.  During the last few decades, an efficient algorithm hasn't been found yet for optimal solution in polynomial time.  Some heuristic algorithms are used to solve job shop scheduling problem.  In this chapter we reviews the literature of job shop scheduling problem.  We categorize job shop scheduling problem into general form and relaxed form.

2.1 Review of job shop scheduling problem with general form

Mascis and Pacciarelli [26] study the job shop scheduling problem with blocking and/or no-wait constraints.  Alessandro and Gianpaolo [15] discuss the machine duplication problem in a job shop with two jobs.  Han [6] focuses on job shop scheduling problem with machine set-up times and time interval due dates.  Steinhöfel, Albrecht, and Wong [21] discuss the job shop scheduling problem under the condition of each task of a job is assigned to a particular machine.  Zäpfel and Wasner [25] discuss the job shop scheduling problem for a supplier of the automotive industry.  Tarantilis and Kiranoudis [9] discuss the job shop scheduling problem for a dehydration plant.  Kumar and Srinivasan [11] address a problem of job shop scheduling for a real-life situation using genetic algorithms.  Yang [19] constructed a job shop scheduling problem to model the operations sequencing in the tree structure and consider the selection of several non-identical parallel machines.  Chang [16] focuses on job shop scheduling problem with consideration of utilization rate and due date.   Ho [20] attempts to minimize max production time by using the genetic algorithm for re-entrant production environment.  Huang [27] addresses a problem of job shop scheduling for no-wait situation.

2.2 Review of job shop scheduling problem with relaxed form

Verhoeven [22] address a problem of job shop scheduling for a resource-constrained scheduling problem.  Dimitris and David [7] consider a relaxation for the job shop scheduling problem called the fluid control problem, in which they replace discrete jobs with the flow of a continuous fluid.  Nuijten and Aarts [8] introduce the multiple capacitated job shop scheduling problem as a generalization of the job shop scheduling problem.  Klaus and Lorant [12] study preemptive and non-preemptive versions of the general multiprocessor job shop scheduling problem.

CHAPTER 3 REVIEW OF CURRENT STATUS

In this chapter we describe the current situation of the engine disassembly process for company A.  We obtain the operation data in order to test our model presented in chapter 4.  There are two sections in this chapter.  They are engine disassembly process and operation data for company A.

3.1 Engine disassembly process

In this section we describe the disassembly process for company A.  Besides disassembly process, we also consider the Clean, NDI, and Bench for parts.  There are 182 steps to disassemble an engine.  Engine disassembly process is one of the tasks of Gate 1.  We combine the steps that are done on the same machine.  That is, they are total 12 meta-steps: (1) Module general remove, (2) FAN general remove, (3) CORE disassembly, (4) HPC rotor disassembly, (5) HPC stator disassembly, (6) CRF disassembly, (7) HPT disassembly, (8) T2N disassembly, (9) HPT rotor disassembly, (10) HPT disassembly, (11) LPT disassembly, and (12) AGB disassembly.  For explanation purpose, we divide Module general remove into three parts (Module general remove-1~3), CORE disassembly into five parts (CORE disassembly-1~5) and HPT disassembly into two parts (HPT disassembly-1~2).  Fig. 3.1 shows the processes of the engine disassembly.  There are two kinds of blocks.  The white one means the disassembly processes.  The black one is the Clean, NDI, and Bench for parts.  There are two kinds of description beside the block.  The right one is the name of the processes.  The bottom one is the machine used or the work center.

Fig. 3.1 The processes of the engine disassembly

3.2 Operation data for company A

In this section we obtain the operation data in order to test our model presented in chapter 4.  There are three parts in this section.  They are standard disassembly process time, definition of working hour and assignment times and the data for machine number and worker demand.

3.2.1Standard disassembly process time

We collect the disassembly data from 2002/1 to 2003/1 in company A to obtain the standard disassembly processes time.  Table 3.1 shows the standard disassembly processes time defined for company A.  While disassembling, modules or parts will be moved to different machines.  The moving time between different machines for modules or parts is included in the predecessor processing time.

Table 3.1 The standard disassembly processes time defined for company A

| Process | Processing time (hours) |
| --- | --- |
| Module general remove-1 | 17 |
| Module general remove-2 | 5.5 |
| Module general remove-3 | 8.5 |
| FAN general remove | 46.76 |
| CORE disassembly-1 | 9.21 |
| CORE disassembly-2 | 4.07 |
| CORE disassembly-3 | 2.04 |
| CORE disassembly-4 | 0.2 |
| CORE disassembly-5 | 1.36 |
| HPC rotor disassembly | 18.55 |
| HPC stator disassembly | 19.31 |
| CRF disassembly | 16.56 |
| HPT disassembly-1 | 3.19 |
| T2N disassembly | 8.51 |
| HPT rotor disassembly | 8.51 |
| HPT disassembly-2 | 8.51 |
| LPT disassembly | 40.46 |
| AGB disassembly | 29.22 |

3.2.2 Definition of working hour and assignment times

Table 3.2 shows the working hour defined for company A.  There are two shifts a day.  Shift 1 is from 8:00 to 17:30.  Shift 2 is from 15:30 to 0:00.  The overlap is from 15:30 to 17:30.  There are 8+7.5-2=13.5 working hours everyday.

Table 3.2 The working hour defined for company A

| Shift | Working time | Working hour |
| --- | --- | --- |
| 1 | 8:00~17:30 | 8 hours (deduct 1.5 hours for lunchtime and rest from working time) |
| 2 | 15:30~0:00 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |

Assignment times for workers equals the numbers of shift.  Because too many assignment times will make a certain degree of trouble (the time of 1 worker assignment is about 1 hour) for the engineer who is in charge of the worker assignments.  It’s important to minimize the total times of doing worker assignments as long as the minimum worker demand is not exceeded.

3.2.3 Machine number and worker demand

Table 3.3 shows the number of disassembly machines and the number of workers for each machine.  “Total worker demand (1 shift a day)” is the sum of the demand of each machines in 1 shift.  “Total worker demand (2 shift a day)” is the double of “Total worker demand (1 shift a day)”.

There are 39 workers in company A that is lower than the theoretical value (48; 2 shifts a day).  Some jobs could not be processed at the same time because they have a specific sequence relationship.  When the specific process is done, workers can support the successor process if they do not work over 8 hours a day.  However, the current 39 workers into work over 8 hours a day since there is a shortage of manpower.

Table 3.3 The number of the disassembly machine and the workers demand in company A

| Machine | Machine Number | Worker Demand |
| --- | --- | --- |
| GANTRY | 4 | 4 |
| Fan stand | Many | 3 |
| PIT | 1 | 3 |
| HPC rotor stand | 6 | 2 |
| HPT stand | 1 | 2 |
| HPT rotor stand | 1 | 2 |
| CRF stand | 2 | 2 |
| LPT stand | 1 | 2 |
| AGB stand | 8 | 2 |
| General stand | Many | 2 |
| Total worker demand (1 shift a day) |  | 24 |
| Total worker demand (2 shifts a day) |  | 48 |
| Disassembly workers in company A (2 shifts a day) |  | 39 |

CHAPTER 4 A MIXED INTEGER PROGRAMMING MODEL FOR ENGINE DISASSEMBLY PROCESS

In this section we develop a mixed integer programming model for engine disassembly processes.  This model contains two parts, namely, sub-model 1 and sub-model 2.  Sub-model 1 determines the earliest disassembly time for engines.  Sub-model 2 determines the minimum worker demand for system.  The inputs of sub-model 2 are the outputs of sub-model 1 multiplied by the numbers of worker of operation machines.

We can’t consider the earliest disassembly time for engines and the minimum worker demand for system simultaneously in one model for the following reasons.  We consider three kinds of rotations, namely, tikms, xikms and tk.  tikms means the starting time for job k of engine i worked worker m on shift s.  xikms means the binary variable indicating whether job k of engine i worked worker m on shift s.  xikms = 1 if job k of engine i is scheduled to be worked by worked worker m on shift s, and xikms = 0 otherwise.  tk means the processing time for job k.  With m=1~3, s=1~2, equation (4-1) states that starting time of job k+1 could not exceed the finish time of job k for engine i.  Equation (4-2) ensures that job k of engine i must be done by only one worker m on shift s.  When we attempt to combine the relationship between (4-1) and (4-2), we can only consider the job or the worker.  Formulate both of the one model is impractical.  To ensure the feasibility of the formulation, the minimum worker demand for system will be calculated after the earliest disassembly time is determined.  In this research the minimum requiring number of workers who work on the time slot for sub-model 2 is the output of sub-model 1 (scheduling result) multiplied by the numbers of worker of operation machines.

m=13s=12ti(k+1)ms−m=13s=12tikms≥tk 　　　　　　                                                  (4-1)

m=13s=12xikms=1                                                                              (4-2)

4.1 A mixed integer programming formulation for sub-model 1

Notations

The following notations are used in the mixed integer programming formulation.

tijk: the starting time for job k of engine i to be processed on machine j;

xijk: the binary variable indicating whether job k of engine i is scheduled on machine j.  xijk = 1 if job k of engine i is scheduled to be processed on machine j, and xijk= 0 otherwise;

sjii'k: the binary variable indicating whether the starting time of job k of engine i is scheduled on machine j is earlier than that of engine i'(the sequence of i' is after i).sjii'k = 0 if the starting time of job k of engine i is scheduled to be processed on machine j is earlier than that of engine i', and sjii'k= 1 otherwise;

cjii'k: the binary variable indicating whether job k of engine i is scheduled on machine j is the same as engine i' (the sequence of i' is after i).  cjii'k = 0 if job k of engine i is scheduled on machine j is the same as that of engine i', and cjii'k= 1 otherwise;

I : the set of all engines;

J : the set of all machines;

C: the subset of set J.  It’s the set that there are more than one machine of that type;

Cu: the uth subset of set C (u=1,2..,n.  n is the number of machine type).  It’s the set that there are more than one machine of that type;

A: the subset of set J.  It’s the set that there is only one machine of that type;

K : the set of all jobs;

B: the set of pairs (j, k), which is job k to be processed on machine j;

Bs: the subset of set B.  It’s the set of job k that have successor one to be processed on machine j;

Bns: the subset of set B.  It’s the set of job k that have no successor one to be processed on machine j;

Ba: the subset of set B.  It’s the set of the first job k for machine j;

Bo: the subset of set B.  It’s the set of job k to be processed on machine j that there is only one of that type;

D: the set of pairs (k, k’), k is the predecessor job for k’;

tk : the processing time for job k;

tj : the operation time to process continuously the same engine for machine j;

M : a large number.

Formulations

Minimizej,k∈Bsi∈Itijk+j,k∈Bnsi∈IMtijk                                   (4-3)

tij'k'−tijk≥tk, for i∈I and for(k,k')∈(k,k')|(k,k')∈D,(j',k')∈B0,(j,k)∈B (4-4)

jxijk=1, for i∈I and for (j,k)∈(j,k)|(j,k)∈Ba,j∈Cu(u=1,2..,n)      (4-5)

tijk−Mxijk'≤0, for i∈I and for j∈j|j∈C,(j,k)∈B,(j,k')∈Ba          (4-6)

j'tij'k'−jtijk≥tk,for i∈I and for (k,k')∈(k,k')|(k,k')∈D,(j',k'),(j,k)∈B,j',j∈Cu(u=1,2..,n)         (4-7-a)

j'tij'k'−tijk≥tk,for i∈I and for (k,k')∈(k,k')|(k,k')∈D,(j',k'),(j,k)∈B,j'∈Cu(u=1,2..,n),j∈A       (4-7-b)

tijk−ti'jk−Msjii'k≤−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈A                                      (4-8)

ti'jk−tijk+Msjii'k≤M−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈A                                      (4-9)

xijk+xi'jk+cjii'k≤2, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C (4-10)

tijk−ti'jk−Msjii'k−Mcjii'k≤−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈C                                     (4-11)

ti'jk−tijk+Msjii'k−Mcjii'k≤M−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈C                                     (4-12)

xijk {0, 1}, for  i∈I and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C             (4-13)

sjii'k {0, 1}, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈J      (4-14)

cjii'k {0, 1}, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C      (4-15)

tijk≥0, for  i∈I and for(j,k)∈B                                  (4-16)

The objective function seeks to minimize the sum of all jobs starting time that have successor one and the sum of the others starting time that is multiplied by a large number.  Because Gate 2 starts after any disassembly job that has no successor one is done, the starting time of that should be done as soon as possible.  In order to speed up the process for Gate 2, a large number is used to multiply all the jobs that have no successor ones.

The constraints (4-4) state that starting time of successor job j’ could not exceed finish time of any job j if the successor one is processed on a machine that is the only one of that type.  The constraints (4-5), (4-6) and (4-7) ensure that every job must be done on only one machine under the condition that there are more than one machine of that type.  The constraints (4-6) ensure that the starting timetijkshould be zero if job j is not operated on machine k.  The constraints (4-7) state that starting time of successor job j’ could not exceed finish time of any job j.  The constraints (4-8) and (4-9) ensure that one job should precede another if two jobs are scheduled on the same machine under the condition that there is only one machine of that type.  If sjii’k =0,the constraints (4-8) indicate that the starting time for job k of engine i' processed on machine j does not exceed the finish time for job k of engine i processed on machine j and the constraints (4-9) are relaxed.  If sjii’k =1,the constraints (4-9) indicate that the starting time for job k of engine i processed on machine j does not exceed the finish time for job k of engine i' processed on machine j and the constraints (4-8) are relaxed.  The constraints (4-10), (4-11) and (4-12) ensure that any job should precede another if two jobs are scheduled on the same machine under the condition that there are more than one machine of that type.  If cjii’k =0,the constraints (4-10) indicate that two jobs are scheduled on the same machine, and cjii’k = 1 otherwise.  cjii’k =0 and sjii’k =0 means the starting time for job k of engine i' processed on machine j does not exceed the finish time for job k of engine i processed on machine j in constraints (4-11) and the constraints (4-12) are relaxed.  cjii’k =0 and sjii’k =1 means the starting time for job k of engine i processed on machine j does not exceed the finish time for job k of engine i' processed on machine j in constraints (4-12) and the constraints (4-11) are relaxed.

4.2 A mixed integer programming formulation for sub-model 2

Notations

The following notations are used in the mixed integer programming formulation.

mi : the number of workers who start to work on the shift i;

ki : the binary variable indicating whether the worker is scheduled on time slot i. ki= 1 if the worker is scheduled on time slot i, andki= 0 otherwise;

minmen : the number of the minimum worker demand for system;

hk: the minimum requiring number of workers who work on the time slot k.  This is the output of sub-model 1 (scheduling result) multiplied by the numbers of worker of operation machines;

I : the set of shifts;

K : the set of time slot;

j : the shift number in a day;

Hk: the set of shifts in time slot k;

X: the set of a sequence (1,2,3...n).  n is the value up to the next larger integer one when total shift number divided by shift number in a day;

r : the impact factor of the worker training and rest for the system.  In company A, which is 0.9016(0.9016=1*0.92(for rest)*0.98(for training));

M : a large number.

Formulations

minZ=Mminmen+i∈Iki　          　　　　　　　 　　　  　　 (4-17)

i∈Hkmi≥hk,∀k∈K     　                                        (4-18)

mi×j−j+1+mi×j−j+2+......+mi×j−r×minmen0,∀i∈X                   (4-19)

Mki−mi≥0,∀i∈I                                              (4-20)

mi≥0 and integer,∀i∈I                                         (4-21)

ki {0, 1}, ∀i∈I                                              (4-22)

The objective function seeks to minimize the worker demand and the total times of doing worker assignments.  In order to emphasize the importance of the worker demand, a large number is used to multiply minmen.

The constraints (4-18) ensure that the number of workers who work on the time slot k should not be less than the minimum requiring number of workers.  The constraints (4-19) ensure that workers will not work over 8 hours continuously.  The constraints (4-20) guarantee that ki=1 if any worker is assigned to shift i.

CHAPTER 5 SOLUTIONS FOR THE ENGINE DISASSEMBLY PROCESS

We solve the proposed models using the CPLEX solver.  There are six parts in this chapter.  They mean six kinds of testing policies as shown in Table 5.1.    Overlap for our test means an engine can start to be disassembled when the last one is processed as long as the minimum worker demand is not exceeded the current available manpower.

Table 5.1 The six parts in Chapter 5

|  | One-engine | Multi-engine | Non-overlap | Overlap | 2 shift a day | 8 shift a day |
| --- | --- | --- | --- | --- | --- | --- |
| Test 1 | √ |  |  |  | √ |  |
| Test 2 | √ |  |  |  |  | √ |
| Test 3 |  | √ | √ |  | √ |  |
| Test 4 |  | √ | √ |  |  | √ |
| Test 5 |  | √ |  | √ | √ |  |
| Test 6 |  | √ |  | √ |  | √ |

Table 5.2~3 show the summary of solutions in this Chapter.  First, we test our model under the condition of one-engine.  Second, we test our model under the condition of multi-engine.  Table 5.2 shows that the 8 shifts a day policy is much better than the 2 shift a day policy under the condition of one-engine.  With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  It brings a better benefit for a company.  Table 5.3 shows that the overlap cases can speed up the finished time for engine disassembly compared with non-overlap cases.

We can suggest company A a policy in order to promote the efficiency.  Compared with the current situation, changes contain two parts.  First, overlap of the engine disassembly process with multi-engine situation defined by this research is allowed.  Second, there are eight shifts a day.  It also can speed up the finished time for engine disassembly under the condition that the require worker demand is not exceeded the current available manpower.

Table 5.2 Summary of solutions under the condition of one-engine

|  |  |  | Model solution | Current situation value | Improvement percentage |
| --- | --- | --- | --- | --- | --- |
| The time that engine 1 is done (hours) |  |  | 77.76 | 81 | 4.0 |
| 2 shifts a day |  | Worker demand (numbers) | 37 | 39 | 5.1 |
|  |  | Assignment times (times) | 12 | 12 | 0.0 |
| 8 shifts a day | Worker demand (numbers) |  | 35 | 39 | 10.3 |
|  | Assignment times (times) |  | 14 | 12 | -16.7 |

Table 5.3 Summary of solutions under the condition of multi-engine

| 2 engines |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Model solution | Current situation value | Improvement percentage |
| The time that the last engine is done (hours) | Non-overlap | 2 shifts a day | 155.52 | 162 | 4.0 |
|  |  | 8 shifts a day | 155.52 | 162 | 4.0 |
|  | Overlap | 2 shifts a day | 129.76 | 162 | 19.9 |
|  |  | 8 shifts a day | 125.76 | 162 | 22.4 |
| Worker demand (numbers) | Non-overlap | 2 shifts a day | 37 | 39 | 5.1 |
|  |  | 8 shifts a day | 35 | 39 | 10.3 |
|  | Overlap | 2 shifts a day | 39 | 39 | 0.0 |
|  |  | 8 shifts a day | 39 | 39 | 0.0 |
| Assignment times (times) | Non-overlap | 2 shifts a day | 23 | 24 | 4.2 |
|  |  | 8 shifts a day | 26 | 24 | -8.3 |
|  | Overlap | 2 shifts a day | 20 | 24 | 16.7 |
|  |  | 8 shifts a day | 20 | 24 | 16.7 |
| 3 engines |  |  |  |  |  |
|  |  |  | Model solution | Current situation value | Improvement percentage |
| The time that the last engine is done (hours) | Non-overlap | 2 shifts a day | 233.28 | 243 | 4.0 |
|  |  | 8 shifts a day | 233.28 | 243 | 4.0 |
|  | Overlap | 2 shifts a day | 181.76 | 243 | 25.2 |
|  |  | 8 shifts a day | 177.76 | 243 | 26.9 |
| Worker demand (numbers) | Non-overlap | 2 shifts a day | 37 | 39 | 5.1 |
|  |  | 8 shifts a day | 35 | 39 | 10.3 |
|  | Overlap | 2 shifts a day | 39 | 39 | 0.0 |
|  |  | 8 shifts a day | 39 | 39 | 0.0 |
| Assignment times (times) | Non-overlap | 2 shifts a day | 35 | 36 | 2.8 |
|  |  | 8 shifts a day | 38 | 36 | -5.6 |
|  | Overlap | 2 shifts a day | 27 | 36 | 25.0 |
|  |  | 8 shifts a day | 27 | 36 | 25.0 |

CHAPTER 6 CONCLUSIONS AND SUGGESTIONS

6.1 Conclusions

In this research, we consider the engine disassembly process which could be viewed as a job shop scheduling problem.  We develop a mixed integer programming (MIP) model for engine disassembly process.  We solve these models using the CPLEX solver.  To illustrate the applicability of the MIP model, we present a case study on the engine disassembly process taken from an engine maintenance company (company A).  We prove that the solutions of current situation for company A not only can speed up the finish time for engine disassembly, also can minimize worker demand.  The results are satisfactory in terms of both efficiency and quality of the solution.  In addition, we suggest company A a policy in order to promote the efficiency.  Compared with the current situation, changes contain two parts.  First, overlap of the engine disassembly process with multi-engine situation defined by this research is allowed.  Second, there are eight shifts a day.  The solution of modified situation can bring much more benefit for company A.

6.2 Suggestions

Not all engine need to be disassembled completely.  For example, the module could be exchanged with the spare one to speed up the process.  Therefore, we may consider the un-overhaul situation.

Job shop scheduling is a NP-hard problem.  There is probably no efficient procedure for finding exactly optimal schedules.  As the computation time is important for the applicable application, we may consider developing the heuristic algorithm to improve the solutions efficiency.

Future research should concern the constraints of time interval due dates.  The objective of future study may be to develop solution procedures with the goal to minimize the total penalty cost due to earliness and tardiness of the production completion time for the engine disassembly process.

In practice, there are many examples of industrial settings in which the buffer capacity has to be taken into account.  In company A, however, the set up time of machine used is included in the processing time.  Future research could concern the impacts of the set up time.

With the variations of experience, workers have different capabilities for the same job.  Future research should consider the uncertain nature of process time.  Fuzzy theory could be used with uncertain time requirements for a job shop problem.

Nowsdays the scheduling strategy must be able to react to the need of market in a short period of time.  On the other hand, shop floor is full of exceptions; such as equipment breakdowns, tools wearing, defects occurrences, rush orders, order withdrawals, mold damages, engineering changes, manufacturing order changes, power outage, materials /personnel shortage, and ill design problems.  If shop floor scheduling cannot respond to these exceptions, prepared schedules could be inaccurate or not executable.  Therefore, the ability to handle exceptions is viable to feature research.

References

| 1. | Beasley, J. E. and Cao, B., “A Tree Search Algorithm for the Crew Scheduling Problem”, European Journal of Operational Research, Vol. 94, No. 3, pp. 517-526, 1996. |
| --- | --- |
| 2. | Chang, J., “Optimization of aviation pilot scheduling”, master thesis, National Central University, Taoyuan, Taiwan, R. O. C., 1996. (in Chinese) |
| 3. | Using the CPLEX Callable Library, CPLEX Optimization, Inc., 1998. |
| 4. | Weng, W. D., “The Rostering of Crew for Airline Operations: An Equitability System Approach”, master thesis, National Chiao Tung University, Hsinchu, Taiwan, R. O. C., 1997. (in Chinese) |
| 5. | Chen, Y. C., “The planning of airline maintenance manpower supply”, master thesis, National Central University, Taoyuan, Taiwan, R. O. C., 2001. (in Chinese) |
| 6. | Han, C. Y., “ Analysis of Genetic Algorithms for Job Shop Scheduling Problem with Set-up Time and Time Interval Due-date”, master thesis, Yuan Ze University, Taoyuan, Taiwan, R. O. C., 2001. (in Chinese) |
| 7. | Bertsimas, D. and Gamarnik, D., “Asymptotically Optimal Algorithms for Job Shop Scheduling and Packet Routing”, Journal of Algorithms, Vol. 33, No. 2, pp. 296-318, 1999. |
| 8. | Nuijten, W. P. M. and Aarts, E. H. L., “A computational study of constraint satisfaction for multiple capacitated job shop scheduling”, European Journal of Operational Research, Vol. 90, No. 2, pp. 269-284, 1996. |
| 9. | Tarantilis, C. D. and Kiranoudis, C. T., “A list-based threshold accepting method for job shop scheduling problems”, International Journal of Production Economics, Vol. 77, No. 2, pp. 159-171, 2002. |
| 10. | Sabuncuoglu, I. and Bayiz, M., “Job shop scheduling with beam search”, European Journal of Operational Research, Vol.118, No. 2, pp. 390-412, 1999. |
| 11. | Kumar, N. S. Hemant and Srinivasan, G., “A genetic algorithm for job shop scheduling - A case study”, Computers in Industry, Vol. 31, No. 2, pp. 155-160, 1996. |
| 12. | Jansen, K. and Porkolab, L., “Polynomial time approximation schemes for general multiprocessor job shop scheduling”, Journal of Algorithms, Vol. 45, No. 2, pp. 167-191, 2002. |
| 13. | Carlier, J. and Pison, E., “An algorithm for solving the job-shop problem”, Management Science, Vol. 35, pp. 167-176, 1989. |
| 14. | Lenstra, J., “Sequencing by enumerative method”, Technical Report, Mathematical Center Tract 69, Mathematisch Centrum, 1976. |
| 15. | Agnetis, A. and Oriolo, G., “The Machine Duplication Problem in a Job Shop with Two Jobs”, International Transactions in Operational Research, Vol. 2, No. 1, pp. 45-60, 1995. |
| 16. | Chang, Y. C., "Job Shop Scheduling with Due Date and Utilization Consideration”, master thesis, National Yunlin University of Science & Technology, Yunlin, Taiwan, R. O. C., 1998. (in Chinese) |
| 17. | Hsu, J. L., “Impact of Lot-Streaming in Job Shop Production System”, master thesis, Da-Yeh University, Changhua, Taiwan, R. O. C., 2000. (in Chinese) |
| 18. | Hsiao, Y. M., “Application of Genetic Algorithm in Job-Shop Scheduling”, master thesis, Yuan Ze University, Taoyuan, Taiwan, R. O. C., 2000. (in Chinese) |
| 19. | Yang, F. C., “Ant Colony Optimization Based Extended Job Shop Scheduler”, master thesis, Nation Taiwan University, Taipei, Taiwan, R. O. C., 2002. (in Chinese) |
| 20. | Ho, C. H., “Research on the Hybrid Genetic Algorithm in Re-entrant Job Shop Problem ”, master thesis, Nation Taiwan University of Science & Technology, Taipei, Taiwan, R. O. C., 2000. (in Chinese) |
| 21. | Steinhöfel, K., Albrecht, A. and Wong, C.K., “ Fast parallel heuristics for the job shop scheduling problem”, Computers and Operations Research, Vol. 29, pp. 151-169, 2002. |
| 22. | Verhoeven, “ Tabu search for resource-constrained scheduling”, European Journal of Operational Research, Vol. 106, pp. 266-276, 1998. |
| 23. | Lenstra J. K., Rinnooy Kan A. H. G. and Brucker P., “Complexity of machine scheduling problem”, Annals of Discrete Mathematics, Vol. 1,pp.343-362, 1977. |
| 24. | Gray M. R. and Johnson D. S., “ Computers and Intractability: A Guide to the Theory of NP-Completeness”, Freeman, San Francisco, 1979. |
| 25. | Zäpfel, G. and Wasner, M., “ A heuristic solution concept for a generalized machine sequencing problem with an application to radiator manufacturing”, International Journal of Production Economics, Vol. 68, pp. 199-213, 2000. |
| 26. | Mascis, A. and Pacciarelli, D., “Job-shop scheduling with blocking and no-wait constraints”, European Journal of Operational Research, Vol. 143, No. 3, pp. 498-517, 2002. |
| 27. | Huang, H. C., “A Hybrid Genetic Algorithm for No-Wait Job Shop Problems”, master thesis, Nation Taiwan University of Science & Technology, Taipei, Taiwan, R. O. C., 2002. (in Chinese) |