CHAPTER 1 INTRODUCTION

1.1 Research Motivations

The developing of aviation industry, a strategic industry with advance technology, is the key point for the whole industry.  In order to be globally competitive, many countries are eager to find out innovative ways to improve the development efficiency.  The engine maintenance schedule is one of the concerned issues.

Due to the fast advanced technology movement, the competence of an enterprise is partly shifted to the capability of aligning the operations management.  It is important to effectively integrate the current technologies and human resources while aided with assistance from the related coordinating measures.  Under the presumption of finite resources, an efficient engine maintenance schedule for a company can reduce the operation cost and expand the business.

If engine maintenance schedule does not take into consideration during early analysis and planning phase, not only increased risk on the operation, cost efficiency are also greatly sacrificed.  In order to establish an advantageous operation environment for engine maintenance schedule and in turn enhance the competitive edge of the company in the worldwide market, company must have an efficient engine maintenance schedule.  In this research, we discuss the engine disassembly process for a company, which is one of the tasks of engine maintenance process.

1.2 Briefing of the current operation

The operations in the engine maintenance company can be divided into four stages: Gate 0, Gate 1, Gate 2 and Gate 3.  At Gate 0, document including engine work scope and work order must be prepared.  At Gate 1, the engine is disassembled and prepared for maintenance.  At Gate 2, the disassembled parts are maintained in the company.  Some of them will be shipped to outside vender if necessary.  At Gate 3, all parts of engine are gathered and assembled.

The major five modules for an engine include FAN module, HPC module, HPT module, LPT module, and AGB module, as shown in Fig. 1.1.  HPC module includes CRF, rotor and stator part.  HPT module includes T2N, rotor and stator part.  LPT module includes rotor and stator part.  The combination of HPC and HPT module is called the Core module.

LPT

AGB

FAN

HPC

HPT

Core module

Fig. 1.1 Aircraft engine

1.3 Research Objectives

We schedule the engine disassembly process.  The suitable solution not only can minimize the disassembly time for engines, also can minimize worker demand for system.

1.4 Research Scope

We discuss the engine disassembly processes for a company.  There are three kinds of disassembly levels, namely, minimum, performance and overhaul.  Minimum means the engine disassembly for exterior inspection.  Performance means some module of the engine should be disassembled completely.  Overhaul means every module of the engine should be disassembled completely.  In this research all of the disassembly engines are in overhaul situation.

1.5 Organization

The organization of this thesis is as follows.  Chapter 2 reviews the literature of related research work.  Chapter 3 describes the current status of the engine disassembly process for a specific company in Taiwan (called company A in this thesis).  Chapter 4 presents a mixed integer programming (MIP) model for engine disassembly process.  Chapter 5 illustrates the solutions for the engine disassembly process case described in chapter 3.  Finally, the conclusions and the future research suggestions are discussed in chapter 6.

CHAPTER 2 LITERATURE REVIEW

Up to present, most related literature merely describes the concepts of engine disassembly process and very few focuses specifically on the scheduling analysis.  This situation is due to business secret for a company.  Because an efficient engine maintenance schedule for a company can reduce the operation cost and expand the business, there are very few public literatures.

We consider the engine disassembly process, which could be viewed as a job shop scheduling problem.  The elements of a job shop scheduling problem consists of a set of machines and a collection of jobs to be scheduled.  Some jobs have to be finished before others can be started and two jobs requiring the same machine cannot be done simultaneously.  The objective is to find a schedule that minimizes the overall completion time of all activities.

Job shop scheduling is a NP-hard problem (Lenstra et al. [23]; Gray and Johnson [24]) that means the probability of finding an efficient procedure for optimal solution is low.  During the last few decades, an efficient algorithm hasn't been found yet for optimal solution in polynomial time.  Some heuristic algorithms are used to solve job shop scheduling problem.

In this chapter we reviews the literature of job shop scheduling problem.  We categorize job shop scheduling problem into general form and relaxed form.  The general form of job shop scheduling problem is described as follows.  The problem is to find the schedule that minimizes the overall completion time that is called the makespan.  All jobs subject to the following constraints:(1) the precedence of tasks given by each job are to be respected, (2) each machine can perform at most one task at a time, (3) the operations cannot be interrupted [9]. The relaxed form of job shop scheduling problem means the relaxation of above constraints.  For instance the processing of any task is allowed to be interrupted any time.

2.1 Review of job shop scheduling problem with general form

Mascis and Pacciarelli [26] study the job shop scheduling problem with blocking and/or no-wait constraints.  With a blocking constraint a job, having completed processing on a machine, remains on it until the next machine becomes available for processing.  A no-wait constraint occurs when two consecutive operations must be performed without any interruption.  They use the alternative graph formulation to model the blocking and no-wait constraints.  They show that several key properties, used to design heuristic procedures, do not hold in the blocking and no-wait cases, while some of the most effective ideas used to develop branch and bound algorithms can be easily extended.  Computational testing is performed to solve the several particular cases.

Alessandro and Gianpaolo [15] discuss the machine duplication problem in a job shop with two jobs.  This problem indicates that there are two jobs, m machines, the machines are not ordered.  The two jobs can start being performed in parallel, until both of them require the same machine.  The problem arises of deciding which job must be processed first, in order to minimize completion time of the two jobs.  In a class of special cases, it can be solved in polynomial time by a dynamic programming algorithm.  A heuristic based on such an algorithm is proposed for the general problem.  They show that their algorithm performs well for the instances.

Han [6] focuses on job shop scheduling problem with machine set-up times and time interval due dates.  The objective of this study is to minimize the total penalty cost due to earliness and tardiness of the production completion time.  A linear integer programming model to the target problem is presented in the research and can be solved by solver when the problem size is small.  For large size problems, he tries to solve the job shop scheduling problem using genetic algorithms with different combinations of methods of encoding.

Steinhöfel, Albrecht, and Wong [21] discuss the job shop scheduling problem under the condition of each task of a job is assigned to a particular machine.  The tasks have to be processed during an uninterrupted time period of a fixed length on a given machine.  The objective is to minimize the overall completion time.  In order to obtain a certain speed-up of computations by using multiprocessor systems, they apply parallel algorithms to the time-consuming part of several heuristics for the job shop scheduling.  They prove that a significant speed-up can be obtained compared to heuristics running on a single processor.

Zäpfel and Wasner [25] discuss the job shop scheduling problem for a supplier of the automotive industry.  The problem is described by a mixed integer programming model.  An approximative search-based algorithm is developed for the problem.  Simulation results that show the quality level of the approximative scheme are reported.  The results show that algorithm has practical benefits in the manufacturing processes.

Tarantilis and Kiranoudis [9] discuss the job shop scheduling problem for a dehydration plant.  The job shop scheduling problem can be represented in terms of a disjunctive graph.  The schedule on a disjunctive graph G consists of finding a set of orientations that minimizes the length of the longest path (critical path).  They develop a new meta-heuristic method for solving the job shop scheduling problem, termed as list-based threshold accepting (LBTA) method.  The LBTA is based on the threshold accepting algorithm.  A real-world case study is presented to illustrate the effectiveness of the proposed approach.

Kumar and Srinivasan [11] address a problem of job shop scheduling for a real-life situation using genetic algorithms.  The objective is to minimize the completion time of the last job on its last machine.  The approach uses different dispatching rule, for different situations and improves the solution using genetic algorithm.  The proposed algorithm yields an improvement of about 30% in makespan over the present system.

Yang [19] constructed a job shop scheduling problem to model the operations sequencing in the tree structure and consider the selection of several non-identical parallel machines.  He tries to solve the job shop scheduling problem using ant colony optimization.  The characteristic of ant colony optimization is that each test will keep the good solution previously and try to find the better one.  For extended job shop scheduling problems, he uses artificial examples to test the efficiency of this algorithm.  Experiment results show that algorithm has practical benefits in the manufacturing processes.

Chang [16] focuses on job shop scheduling problem with consideration of utilization rate and due date.   The objective minimizes total tardiness and maximizes the utilization rate.  He uses tabu-based algorithm to solve the job shop problem with two objectives.  Experiment results show that algorithm has practical benefits in the manufacturing processes.

Ho [20] attempts to minimize max production time by using the genetic algorithm for re-entrant production environment.  The re-entrant production environment means in the process of production will repeatedly use the same machine.  Experiment results show that algorithm has practical benefits in the manufacturing processes.

Huang [27] addresses a problem of job shop scheduling for no-wait situation.  The no-wait case, that is, every job has its own processing sequence with the constraint that no waiting time is allowed between operations within any job.  He uses genetic -based algorithm to solve the job shop problem.  Experiment results, which are solved from well-known job shop instances, show that algorithm has practical benefits in the manufacturing processes.

2.2 Review of job shop scheduling problem with relaxed form

Verhoeven [22] address a problem of job shop scheduling for a resource-constrained scheduling problem.  In this problem machines are capable of processing several operations simultaneously.  Operations may require multiple resources for processing with different processing times on each resource.  He presented a tabu search algorithm for this problem.  Experiment results, which are solved from well-known job shop instances, show that algorithm has practical benefits in the manufacturing processes.

Dimitris and David [7] consider a relaxation for the job shop scheduling problem called the fluid control problem, in which they replace discrete jobs with the flow of a continuous fluid.  Machines are allowed to work simultaneously on several types of jobs.  The objective is to minimize the makespan.  They present asymptotically optimal algorithms for the job shop scheduling problem.  Experiment results, which are solved from well-known job shop instances, show that their algorithms produce schedules that are within 1% of optimality even for moderately sized problems.

Nuijten and Aarts [8] introduce the multiple capacitated job shop scheduling problem as a generalization of the job shop scheduling problem.  In this problem machines may process several operations simultaneously.  A machine can simultaneously process only those sets of operations whose sizes do not exceed the capacity of the machine.  They present an algorithm based on constraint satisfaction techniques that is based on the tree search algorithms.  An empirical performance analysis is performed using a well-known set of instances of the job shop scheduling problem.  They show that their algorithm performs well for the instances.

Klaus and Lorant [12] study preemptive and non-preemptive versions of the general multiprocessor job shop scheduling problem.  The preemptive case, that is, the processing of any task is allowed to be interrupted any time at no cost and restarted later.  The non-preemptive version of the problem, where a task—once started—has to be completed without interruption.  The problem is described by a mixed integer programming model.  They proposed linear time approximation schemes for the general multiprocessor job shop scheduling problem with makespan minimization that posses a polynomial time approximation scheme.  They compute approximate solutions for some special cases.  These results include many recent developments on polynomial time approximation schemes for scheduling jobs.

2.3 Summary

Because most related literature merely describe the concepts of engine disassembly process and very few focuses specifically on the scheduling analysis, we consider the engine disassembly process which could be viewed as a job shop scheduling problem.

Up to present, there are not related literature describe the concepts of　engine disassembly process.  The models presented by the past literatures are not suitable for engine disassembly process.  Therefore, we develop a mixed integer programming (MIP) model for engine disassembly process.

As a matter of fact, only small size instances of the job shop problem can be solved with a suitable computational time by exact algorithms [13,14].  For large instances, important results have been recently achieved by heuristic methods.  Nevertheless, the lack of their flexibility when the formulation of the problem changes, their unsuitability for experimentation, and the fact that they were not able to produce high quality solutions very often.  On the other hand, the complexity of the engine disassembly process problem is not analyzed by past research.  Because an efficient engine disassembly schedule for a company can reduce the operation cost and expand the business, in this thesis we attempt to develop a model to improve the efficiency for this problem with exact algorithm.

CHAPTER 3 REVIEW OF CURRENT STATUS

In this chapter we describe the current situation of the engine disassembly process for company A.  We obtain the operation data in order to test our model presented in chapter 4.  There are two sections in this chapter.  They are engine disassembly process and operation data for company A.

3.1 Engine disassembly process

In this section we describe the disassembly process for company A.  Besides disassembly process, we also consider the Clean, NDI, and Bench for parts.

There are 182 steps to disassemble an engine.  Engine disassembly process is one of the tasks of Gate 1.  We combine the steps that are done on the same machine.  That is, they are total 12 meta-steps: (1) Module general remove, (2) FAN general remove, (3) CORE disassembly, (4) HPC rotor disassembly, (5) HPC stator disassembly, (6) CRF disassembly, (7) HPT disassembly, (8) T2N disassembly, (9) HPT rotor disassembly, (10) HPT disassembly, (11) LPT disassembly, and (12) AGB disassembly.

Besides disassembly process, we also consider the Clean, NDI, and Bench for parts in this research.  In company A, the starting time of Clean, NDI, and Bench for parts begins when the module general remove is done.  Clean means the remove of the dirty substance on the engine parts.  NDI means non-damaged inspection.  Bench means detailed investigation of the performance.

For explanation purpose, we divide Module general remove into three parts (Module general remove-1~3), CORE disassembly into five parts (CORE disassembly-1~5) and HPT disassembly into two parts (HPT disassembly-1~2).

Fig. 3.1 shows the processes of the engine disassembly.  There are two kinds of blocks.  The white one means the disassembly processes.  The black one is the Clean, NDI, and Bench for parts.  There are two kinds of description beside the block.  The right one is the name of the processes.  The bottom one is the machine used or the work center.

Fig. 3.1 The processes of the engine disassembly

The processes of the engine disassembly begin at Module general remove-1 that is processed on GRANTY.  After Module general remove-1, there are two parts.  First part is Module general remove-2 that is processed on GRANTY and second part is AGB disassembly that is processed on AGB stand.  After Module general remove-2, there are two parts.  First part is Module general remove-3 that is processed on GRANTY and second part is LPT disassembly (includes LPT stator and rotor disassembly) that is processed on LPT stand.  After Module general remove-3, there are three parts.  First part is Clean, NDI and Bench processes that is processed on Clean, NDI and Bench center, second part is FAN general remove that is processed on FAN stand and third part is CORE disassembly-1 that is processed on PIT.

After CORE disassembly-1, there are two parts.  First part is CORE disassembly-2 that is processed on PIT and second part is HPT disassembly-1 (includes HPT stator disassembly) that is processed on HPT stand.  After CORE disassembly-2, there are two parts.  First part is CORE disassembly-3 that is processed on PIT and second part is HPC stator disassembly that is processed on general stand.  After CORE disassembly-3, there are two parts.  First part is CORE disassembly-4 that is processed on PIT and second part is CRF disassembly that is processed on CRF stand.  After CORE disassembly-4, there are two parts.  First part is CORE disassembly-5 that is processed on PIT and second part is HPC rotor disassembly that is processed on HPC rotor stand.

After HPT disassembly-1 (includes HPT stator disassembly), there are three parts.  First part is T2N disassembly that is processed on HPT stand, second part is HPT rotor disassembly that is processed on HPT rotor stand and third part is HPT disassembly-2 that is processed on HPT stand.  After T2N and HPT rotor are disassembled, the third part will continue to be disassembled.

3.2 Operation data for company A

In this section we obtain the operation data in order to test our model presented in chapter 4.  There are three parts in this section.  They are standard disassembly process time, definition of working hour and assignment times and the data for machine number and worker demand.

3.2.1Standard disassembly process time

We collect the disassembly data from 2002/1 to 2003/1 in company A to obtain the standard disassembly processes time.  Table 3.1 shows the standard disassembly processes time defined for company A.  Because each engine has different time to be disassembled completely, the engineer who is in charge of the engine scheduling, suggests us using the average of the top one-half of the processing time with overhaul situation to decide the standard disassembly processing time for AGB, LPT, HPT, and CORE module.  Because the precision gap of module general remove data is too large to decide it, the engineer estimates 31 hours are required for the process.  For FAN general remove, because there is no data for overhaul situation, the engineer suggests us using the average of the top one-quarter of the total processing time.

While disassembling, modules or parts will be moved to different machines.  The moving time between different machines for modules or parts is included in the predecessor processing time.

Table 3.1 The standard disassembly processes time defined for company A

| Process | Processing time (hours) |
| --- | --- |
| Module general remove-1 | 17 |
| Module general remove-2 | 5.5 |
| Module general remove-3 | 8.5 |
| FAN general remove | 46.76 |
| CORE disassembly-1 | 9.21 |
| CORE disassembly-2 | 4.07 |
| CORE disassembly-3 | 2.04 |
| CORE disassembly-4 | 0.2 |
| CORE disassembly-5 | 1.36 |
| HPC rotor disassembly | 18.55 |
| HPC stator disassembly | 19.31 |
| CRF disassembly | 16.56 |
| HPT disassembly-1 | 3.19 |
| T2N disassembly | 8.51 |
| HPT rotor disassembly | 8.51 |
| HPT disassembly-2 | 8.51 |
| LPT disassembly | 40.46 |
| AGB disassembly | 29.22 |

3.2.2 Definition of working hour and assignment times

Table 3.2 shows the working hour defined for company A.  There are two shifts a day.  Shift 1 is from 8:00 to 17:30.  Shift 2 is from 15:30 to 0:00.  The overlap is from 15:30 to 17:30.  There are 8+7.5-2=13.5 working hours everyday.

Table 3.2 The working hour defined for company A

| Shift | Working time | Working hour |
| --- | --- | --- |
| 1 | 8:00~17:30 | 8 hours (deduct 1.5 hours for lunchtime and rest from working time) |
| 2 | 15:30~0:00 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |

Assignment times for workers equals the numbers of shift.  Because too many assignment times will make a certain degree of trouble (the time of 1 worker assignment is about 1 hour) for the engineer who is in charge of the worker assignments.  It’s important to minimize the total times of doing worker assignments as long as the minimum worker demand is not exceeded.

3.2.3 Machine number and worker demand

Table 3.3 shows the number of disassembly machines and the number of workers for each machine.  “Total worker demand (1 shift a day)” is the sum of the demand of each machines in 1 shift.  “Total worker demand (2 shift a day)” is the double of “Total worker demand (1 shift a day)”.

There are 39 workers in company A that is lower than the theoretical value (48; 2 shifts a day).  Some jobs could not be processed at the same time because they have a specific sequence relationship.  When the specific process is done, workers can support the successor process if they do not work over 8 hours a day.  However, the current 39 workers into work over 8 hours a day since there is a shortage of manpower.

Table 3.3 The number of the disassembly machine and the workers demand in company A

| Machine | Machine Number | Worker Demand |
| --- | --- | --- |
| GANTRY | 4 | 4 |
| Fan stand | Many | 3 |
| PIT | 1 | 3 |
| HPC rotor stand | 6 | 2 |
| HPT stand | 1 | 2 |
| HPT rotor stand | 1 | 2 |
| CRF stand | 2 | 2 |
| LPT stand | 1 | 2 |
| AGB stand | 8 | 2 |
| General stand | Many | 2 |
| Total worker demand (1 shift a day) |  | 24 |
| Total worker demand (2 shifts a day) |  | 48 |
| Disassembly workers in company A (2 shifts a day) |  | 39 |

CHAPTER 4 A MIXED INTEGER PROGRAMMING MODEL FOR ENGINE DISASSEMBLY PROCESS

In this section we develop a mixed integer programming model for engine disassembly processes.  This model contains two parts, namely, sub-model 1 and sub-model 2.  Sub-model 1 determines the earliest disassembly time for engines.  Sub-model 2 determines the minimum worker demand for system.  The inputs of sub-model 2 are the outputs of sub-model 1 multiplied by the numbers of worker of operation machines.

We can’t consider the earliest disassembly time for engines and the minimum worker demand for system simultaneously in one model for the following reasons.  We consider three kinds of rotations, namely, tikms, xikms and tk.  tikms means the starting time for job k of engine i worked worker m on shift s.  xikms means the binary variable indicating whether job k of engine i worked worker m on shift s.  xikms = 1 if job k of engine i is scheduled to be worked by worked worker m on shift s, and xikms = 0 otherwise.  tk means the processing time for job k.  With m=1~3, s=1~2, equation (4-1) states that starting time of job k+1 could not exceed the finish time of job k for engine i.  Equation (4-2) ensures that job k of engine i must be done by only one worker m on shift s.  When we attempt to combine the relationship between (4-1) and (4-2), we can only consider the job or the worker.  Formulate both of the one model is impractical.  To ensure the feasibility of the formulation, the minimum worker demand for system will be calculated after the earliest disassembly time is determined.  In this research the minimum requiring number of workers who work on the time slot for sub-model 2 is the output of sub-model 1 (scheduling result) multiplied by the numbers of worker of operation machines.

m=13s=12ti(k+1)ms−m=13s=12tikms≥tk 　　　　　　                                                  (4-1)

m=13s=12xikms=1                                                                              (4-2)

4.1 A mixed integer programming formulation for sub-model 1

Notations

The following notations are used in the mixed integer programming formulation.

tijk: the starting time for job k of engine i to be processed on machine j;

xijk: the binary variable indicating whether job k of engine i is scheduled on machine j.  xijk = 1 if job k of engine i is scheduled to be processed on machine j, and xijk= 0 otherwise;

sjii'k: the binary variable indicating whether the starting time of job k of engine i is scheduled on machine j is earlier than that of engine i'(the sequence of i' is after i).sjii'k = 0 if the starting time of job k of engine i is scheduled to be processed on machine j is earlier than that of engine i', and sjii'k= 1 otherwise;

cjii'k: the binary variable indicating whether job k of engine i is scheduled on machine j is the same as engine i' (the sequence of i' is after i).  cjii'k = 0 if job k of engine i is scheduled on machine j is the same as that of engine i', and cjii'k= 1 otherwise;

I : the set of all engines;

J : the set of all machines;

C: the subset of set J.  It’s the set that there are more than one machine of that type;

Cu: the uth subset of set C (u=1,2..,n.  n is the number of machine type).  It’s the set that there are more than one machine of that type;

A: the subset of set J.  It’s the set that there is only one machine of that type;

K : the set of all jobs;

B: the set of pairs (j, k), which is job k to be processed on machine j;

Bs: the subset of set B.  It’s the set of job k that have successor one to be processed on machine j;

Bns: the subset of set B.  It’s the set of job k that have no successor one to be processed on machine j;

Ba: the subset of set B.  It’s the set of the first job k for machine j;

Bo: the subset of set B.  It’s the set of job k to be processed on machine j that there is only one of that type;

D: the set of pairs (k, k’), k is the predecessor job for k’;

tk : the processing time for job k;

tj : the operation time to process continuously the same engine for machine j;

M : a large number.

Formulations

Minimizej,k∈Bsi∈Itijk+j,k∈Bnsi∈IMtijk                                   (4-3)

tij'k'−tijk≥tk, for i∈I and for(k,k')∈(k,k')|(k,k')∈D,(j',k')∈B0,(j,k)∈B (4-4)

jxijk=1, for i∈I and for (j,k)∈(j,k)|(j,k)∈Ba,j∈Cu(u=1,2..,n)      (4-5)

tijk−Mxijk'≤0, for i∈I and for j∈j|j∈C,(j,k)∈B,(j,k')∈Ba          (4-6)

j'tij'k'−jtijk≥tk,for i∈I and for (k,k')∈(k,k')|(k,k')∈D,(j',k'),(j,k)∈B,j',j∈Cu(u=1,2..,n)         (4-7-a)

j'tij'k'−tijk≥tk,for i∈I and for (k,k')∈(k,k')|(k,k')∈D,(j',k'),(j,k)∈B,j'∈Cu(u=1,2..,n),j∈A       (4-7-b)

tijk−ti'jk−Msjii'k≤−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈A                                      (4-8)

ti'jk−tijk+Msjii'k≤M−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈A                                      (4-9)

xijk+xi'jk+cjii'k≤2, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C (4-10)

tijk−ti'jk−Msjii'k−Mcjii'k≤−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈C                                     (4-11)

ti'jk−tijk+Msjii'k−Mcjii'k≤M−tj, for  i,i'∈I (i<i') and for

(j,k)∈(j,k)|(j,k)∈Ba,j∈C                                     (4-12)

xijk {0, 1}, for  i∈I and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C             (4-13)

sjii'k {0, 1}, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈J      (4-14)

cjii'k {0, 1}, for  i,i'∈I (i<i') and for(j,k)∈(j,k)|(j,k)∈Ba,j∈C      (4-15)

tijk≥0, for  i∈I and for(j,k)∈B                                  (4-16)

The objective function seeks to minimize the sum of all jobs starting time that have successor one and the sum of the others starting time that is multiplied by a large number.  Because Gate 2 starts after any disassembly job that has no successor one is done, the starting time of that should be done as soon as possible.  In order to speed up the process for Gate 2, a large number is used to multiply all the jobs that have no successor ones.

The constraints (4-4) state that starting time of successor job j’ could not exceed finish time of any job j if the successor one is processed on a machine that is the only one of that type.  The constraints (4-5), (4-6) and (4-7) ensure that every job must be done on only one machine under the condition that there are more than one machine of that type.  The constraints (4-6) ensure that the starting timetijkshould be zero if job j is not operated on machine k.  The constraints (4-7) state that starting time of successor job j’ could not exceed finish time of any job j.  The constraints (4-8) and (4-9) ensure that one job should precede another if two jobs are scheduled on the same machine under the condition that there is only one machine of that type.  If sjii’k =0,the constraints (4-8) indicate that the starting time for job k of engine i' processed on machine j does not exceed the finish time for job k of engine i processed on machine j and the constraints (4-9) are relaxed.  If sjii’k =1,the constraints (4-9) indicate that the starting time for job k of engine i processed on machine j does not exceed the finish time for job k of engine i' processed on machine j and the constraints (4-8) are relaxed.  The constraints (4-10), (4-11) and (4-12) ensure that any job should precede another if two jobs are scheduled on the same machine under the condition that there are more than one machine of that type.  If cjii’k =0,the constraints (4-10) indicate that two jobs are scheduled on the same machine, and cjii’k = 1 otherwise.  cjii’k =0 and sjii’k =0 means the starting time for job k of engine i' processed on machine j does not exceed the finish time for job k of engine i processed on machine j in constraints (4-11) and the constraints (4-12) are relaxed.  cjii’k =0 and sjii’k =1 means the starting time for job k of engine i processed on machine j does not exceed the finish time for job k of engine i' processed on machine j in constraints (4-12) and the constraints (4-11) are relaxed.

4.2 A mixed integer programming formulation for sub-model 2

Notations

The following notations are used in the mixed integer programming formulation.

mi : the number of workers who start to work on the shift i;

ki : the binary variable indicating whether the worker is scheduled on time slot i. ki= 1 if the worker is scheduled on time slot i, andki= 0 otherwise;

minmen : the number of the minimum worker demand for system;

hk: the minimum requiring number of workers who work on the time slot k.  This is the output of sub-model 1 (scheduling result) multiplied by the numbers of worker of operation machines;

I : the set of shifts;

K : the set of time slot;

j : the shift number in a day;

Hk: the set of shifts in time slot k;

X: the set of a sequence (1,2,3...n).  n is the value up to the next larger integer one when total shift number divided by shift number in a day;

r : the impact factor of the worker training and rest for the system.  In company A, which is 0.9016(0.9016=1*0.92(for rest)*0.98(for training));

M : a large number.

Formulations

minZ=Mminmen+i∈Iki　          　　　　　　　 　　　  　　 (4-17)

i∈Hkmi≥hk,∀k∈K     　                                        (4-18)

mi×j−j+1+mi×j−j+2+......+mi×j−r×minmen0,∀i∈X                   (4-19)

Mki−mi≥0,∀i∈I                                              (4-20)

mi≥0 and integer,∀i∈I                                         (4-21)

ki {0, 1}, ∀i∈I                                              (4-22)

The objective function seeks to minimize the worker demand and the total times of doing worker assignments.  In order to emphasize the importance of the worker demand, a large number is used to multiply minmen.

The constraints (4-18) ensure that the number of workers who work on the time slot k should not be less than the minimum requiring number of workers.  The constraints (4-19) ensure that workers will not work over 8 hours continuously.  The constraints (4-20) guarantee that ki=1 if any worker is assigned to shift i.

CHAPTER 5 SOLUTIONS FOR THE ENGINE DISASSEMBLY PROCESS

We solve the proposed models using the CPLEX solver.  We write a DELPHI programming code to generate the constraints and variables of these models.  First, we solve sub-model 1 to determine the earliest disassembly time for engines.  Second, we solve sub-model 2 to determine the minimum worker demand.  The inputs of sub-model 2 are the outputs of sub-model 1 multiplied by the numbers of worker of operation machines as shown in Table 3.3.

There are six parts in this chapter.  They mean six kinds of testing policies as shown in Table 5.1.  First, we solve for the solutions under the condition of the one-engine situation with 2 shifts a day policy (That is the current situation for company A under the condition of one-engine).  Second, we solve for the solutions under the condition of the one-engine situation with 8 shifts a day policy.  Third, we solve for the solutions under the condition of the multi-engine situation with non-overlap and 2 shifts a day policy (That is the current situation for company A under the condition of multi-engine).  Fourth, we solve for the solutions under the condition of the multi-engine situation with non-overlap and 8 shifts a day policy.  Fifth, we solve for the solutions under the condition of the multi-engine situation with overlap and 2 shifts a day policy.  Sixth, we solve for the solutions under the condition of the multi-engine situation with overlap and 8 shifts a day policy.  Overlap for our test means an engine can start to be disassembled when the last one is processed as long as the minimum worker demand is not exceeded the current available manpower.

Table 5.1 The six parts in Chapter 5

|  | One-engine | Multi-engine | Non-overlap | Overlap | 2 shift a day | 8 shift a day |
| --- | --- | --- | --- | --- | --- | --- |
| Test 1 | √ |  |  |  | √ |  |
| Test 2 | √ |  |  |  |  | √ |
| Test 3 |  | √ | √ |  | √ |  |
| Test 4 |  | √ | √ |  |  | √ |
| Test 5 |  | √ |  | √ | √ |  |
| Test 6 |  | √ |  | √ |  | √ |

The current situation in company A is described as follows.  Company A estimates 81 hours are required for disassembly process with overhaul case.  Generally, the second engine can’t start to be disassembled until the first one is finished.  That is, the current process of engine disassembly is based on the one by one order.  There are two shifts a day, as shown in Table 3.2.  Shift 1 is from 8:00 to 17:30.  Shift 2 is from 15:30 to 0:00.  The overlap is from 15:30 to 17:30.  There are 13.5 working hours everyday.  Assignment times for workers equals the numbers of shift.  Because company A estimates 81/13.5=6 days are required for disassembly process with overhaul case, assignment times for workers under the condition of an overhaul engine are 2*6=12.  The assignment times for the multi-engine case are a multiple of the assignment times for the one-engine case.

Besides disassembly process, we also consider the Clean, NDI, and Bench for parts.  In company A, the starting time of Clean, NDI, and Bench for parts begins when the module general remove is done.  The total processing time is 80 hours.  The second engine can’t start to Clean, NDI, and Bench until the first one is done.  The working team of Clean, NDI, and Bench does not include in the disassembly team.

5.1 Solutions for one-engine situation with 2 shifts a day policy

In this section we solve for the solutions under the condition of the one-engine situation with 2 shifts a day policy.

5.1.1 The earliest disassembly time for one-engine

We describe the optimal solution of the earliest disassembly time for engines.  Besides disassembly process, we also consider the Clean, NDI, and Bench for parts.

For explanation purpose, the following solutions are represented with the general form, as shown in Fig. 5.1.  The block means different processes.  There are two kinds of blocks.  The white one means the disassembly processes.  The black one is the Clean, NDI, and Bench for parts.  There are two numbers on the left of the block.  The left one means the starting time of the job.  The right one is the processing time of the job.  There are two numbers under the block.  The left one means the machine ID.  The right one is the machine used or the work center.  There are two numbers on the right of the block.  The left one means the name of the process.  The right one is the process ID.

Fig. 5.1 the description of the solutions

Fig. 5.2 shows the optimal solution of one-engine for the earliest disassembly time.  In current situation, the total time to disassemble an overhaul engine is 81 hour.  As shown in Fig. 5.2, the latest disassembly job is process (5) .If we sum the starting time (31 hours) and the processing time (46.76 hours) of process (5), we know the engine could be finished in 77.76 (31+46.76) hours.  It’s better than the current situation (81 hours).  For the members of Clean, NDI and Bench, the work is finished in 31+80=111 hours.  It’s slightly better than the current situation (112 hours).

Fig. 5.2 The optimal solution of one-engine for the earliest disassembly time

5.1.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.2.  The inputs of sub-model 2 are the outputs of sub-model 1 as shown in Fig. 5.2 multiplied by the numbers of worker of operation machines as shown in Table 3.3.  The minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (12 times) are equal to that of the current situation.

Table 5.2 The optimal solution of minimum worker demand for one-engine with 2 shifts a day policy

| The minimum worker demand for system |  | 37 |
| --- | --- | --- |
| Assignment times |  | 12 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 2 | 4 |
| 2 | 1 | 6 |
|  | 2 | 8 |
| 3 | 1 | 10 |
|  | 2 | 12 |
| 4 | 1 | 18 |
|  | 2 | 15 |
| 5 | 1 | 13 |
|  | 2 | 11 |
| 6 | 1 | 3 |
|  | 2 | 3 |

5.1.3 Summary of solutions for one-engine situation with 2 shifts a day policy

Table 5.3 shows the summary of solutions in this section.  For sub-model 1,the engine could be finished in 77.76 hours.  It’s better than the current situation (81 hours).  For sub-model 2, the minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (12 times) are equal to that of the current situation.

Table 5.3 Summary of solutions for the one-engine situation with 2 shifts a day policy (That is the current situation for company A under the condition of one-engine)

|  | Model solution | Current situation value | Improvement percentage |
| --- | --- | --- | --- |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| Worker demand (numbers) | 37 | 39 | 5.1 |
| Assignment times (times) | 12 | 12 | 0.0 |

5.2 Solutions for one-engine situation with 8 shifts a day policy

In this section we solve for the solutions under the condition of the one-engine situation with 8 shifts a day policy.  Table 5.4 shows the definition of 8 shifts a day policy.  There are 8 working hours for shift 1,2,3 and 4.  There are 7.5 working hours for shift 5,6,7 and 8.

Table 5.4 The definition of 8 shifts a day policy

| Shift | Working time | Working hour |
| --- | --- | --- |
| 1 | 8:00~17:30 | 8 hours (deduct 1.5 hours for lunchtime and rest from working time) |
| 2 | 9:00~18:30 | 8 hours (deduct 1.5 hours for lunchtime and rest from working time) |
| 3 | 10:00~19:30 | 8 hours (deduct 1.5 hours for lunchtime and rest from working time) |
| 4 | 11:00~21:00 | 8 hours (deduct 2 hours for lunchtime ,dinnertime and rest from working time) |
| 5 | 13:00~21:30 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |
| 6 | 13:30~22:00 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |
| 7 | 14:30~23:30 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |
| 8 | 15:30~0:00 | 7.5 hours (deduct 1 hour for dinnertime and rest from working time) |

5.2.1 The earliest disassembly time for one-engine

The optimal solution of this section is equal to that of the section 5.1.1.  The engine could be finished in 77.76 hours.  It’s better than the current situation (81 hours).  For the members of Clean, NDI and Bench, the work is finished in 31+80=111 hours.  It’s slightly better than the current situation (112 hours).

5.2.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.5.  The inputs of sub-model 2 are the outputs of sub-model 1 as shown in Fig. 5.2 multiplied by the numbers of worker of operation machines as shown in Table 3.3.  The minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (14 times) are more than the current situation (12 times).  With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  It brings a better benefit for a company.

Table 5.5 The optimal solution of minimum worker demand for one-engine with 8 shifts a day policy

| The minimum worker demand |  | 35 |
| --- | --- | --- |
| Assignment times |  | 14 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 8 | 4 |
| 2 | 1 | 6 |
|  | 8 | 8 |
| 3 | 1 | 10 |
|  | 8 | 12 |
| 4 | 1 | 16 |
|  | 5 | 1 |
|  | 6 | 1 |
|  | 8 | 13 |
| 5 | 1 | 13 |
|  | 8 | 11 |
| 6 | 1 | 3 |
|  | 8 | 3 |

5.2.3 Summary of solutions for one-engine situation with 8 shifts a day policy

Table 5.6 shows the summary of solutions in this section.  For sub-model 1,the engine could be finished in 77.76 hours.  It’s better than the current situation (81 hours).  For sub-model 2, the minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (14 times) are more than the current situation.

Table 5.6 Summary of solutions for the one-engine situation with 8 shifts a day policy

|  | Model solution | Current situation value | Improvement percentage |
| --- | --- | --- | --- |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| Worker demand (numbers) | 35 | 39 | 10.2 |
| Assignment times (times) | 14 | 12 | -16.6 |

5.3 Solutions for multi-engine situation with non-overlap and 2 shifts a day policy

In this section we solve for the solutions under the condition of the multi-engine situation with non-overlap and 2 shifts a day policy.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.

5.3.1 The earliest disassembly time for engines

The optimal solution for the multi-engine case is similar to that of the one-engine case as shown in Fig. 5.2.  Because the second engine can’t start to be disassembled until the first one is finished, the finished time for the multi-engine case is a multiple of the finished time for the one-engine case.  For the second engine case, the second engine could be finished in 77.76(process (5))*2=155.52 hours.  It’s better than the current situation (81*2=162 hours).  For the members of Clean, NDI and Bench, the work is finished in 111*2=222 hours.  It’s slightly better than the current situation (112*2=224 hours).

5.3.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.7~8.  Under the condition of 2 engines, the minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (23 times) are slightly less than the current situation (12*2=24 times).  Under the condition of 3 engines, the minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (35 times) are slightly less than the current situation (12*3=36 times).

Table 5.7 The optimal solution of minimum worker demand for 2 engines situation with non-overlap and 2 shifts a day policy

| The minimum worker demand |  | 37 |
| --- | --- | --- |
| Assignment times |  | 23 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 2 | 4 |
| 2 | 1 | 6 |
|  | 2 | 8 |
| 3 | 1 | 10 |
|  | 2 | 12 |
| 4 | 1 | 18 |
|  | 2 | 15 |
| 5 | 1 | 13 |
|  | 2 | 11 |
| 6 | 1 | 3 |
|  | 2 | 4 |
| 7 | 1 | 4 |
|  | 2 | 4 |
| 8 | 1 | 6 |
|  | 2 | 8 |
| 9 | 1 | 10 |
|  | 2 | 14 |
| 10 | 1 | 18 |
|  | 2 | 15 |
| 11 | 1 | 13 |
|  | 2 | 5 |
| 12 | 1 | 3 |

Table 5.8 The optimal solution of minimum worker demand for 3 engines situation with non-overlap and 2 shifts a day policy

| The minimum worker demand |  | 37 |
| --- | --- | --- |
| Assignment times |  | 35 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 2 | 4 |
| 2 | 1 | 6 |
|  | 2 | 8 |
| 3 | 1 | 10 |
|  | 2 | 12 |
| 4 | 1 | 18 |
|  | 2 | 15 |
| 5 | 1 | 13 |
|  | 2 | 11 |
| 6 | 1 | 3 |
|  | 2 | 4 |
| 7 | 1 | 4 |
|  | 2 | 4 |
| 8 | 1 | 6 |
|  | 2 | 8 |
| 9 | 1 | 10 |
|  | 2 | 14 |
| 10 | 1 | 18 |
|  | 2 | 15 |
| 11 | 1 | 13 |
|  | 2 | 5 |
| 12 | 1 | 3 |
|  | 2 | 4 |
| 13 | 1 | 4 |
|  | 2 | 6 |
| 14 | 1 | 8 |
|  | 2 | 10 |
| 15 | 1 | 10 |
|  | 2 | 18 |
| 16 | 1 | 18 |
|  | 2 | 13 |
| 17 | 1 | 13 |
|  | 2 | 3 |
| 18 | 1 | 3 |

5.3.3 Summary of solutions for multi-engine situation with non-overlap and 2 shifts a day policy

Table 5.9 shows the summary of solutions in this section.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.  Under the condition of 2 engines, the last engine could be finished in 77.76*2=155.52 hours.  It’s better than the current situation (81*2=162 hours).  The minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (23 times) are less than the current situation (24 times).  Under the condition of 3 engines, the last engine could be finished in 77.76*3=233.28 hours.  It’s better than the current situation (81*3=243 hours).  The minimum worker demand (37 workers) is less than the current situation (39 workers).  Assignment times (35 times) are less than the current situation (36 times).

Table 5.9 Summary of solutions for the multi-engine situation with non-overlap and 2 shifts a day policy

| 2 engines |  |  |  |
| --- | --- | --- | --- |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 155.52 | 162 | 4.0 |
| Worker demand (numbers) | 37 | 39 | 5.1 |
| Assignment times (times) | 23 | 24 | 4.2 |
| 3 engines |  |  |  |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 155.52 | 162 | 4.0 |
| The time that engine 3 is done (hours) | 233.28 | 243 | 4.0 |
| Worker demand (numbers) | 37 | 39 | 5.1 |
| Assignment times (times) | 35 | 36 | 2.8 |

5.4 Solutions for multi-engine situation with non-overlap and 8 shifts a day policy

In this section we solve for the solutions under the condition of the multi-engine situation with non-overlap and 8 shifts a day policy.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.

5.4.1 The earliest disassembly time for engines

The optimal solution for the multi-engine case is similar to that of the one-engine case as shown in Fig. 5.2.  Because the second engine can’t start to be disassembled until the first one is finished, the finished time for the multi-engine case is a multiple of the finished time for the one-engine case.  For the second engine case, the second engine could be finished in 77.76(process (5))*2=155.52 hours.  It’s better than the current situation (81*2=162 hours).  For the members of Clean, NDI and Bench, the work is finished in 111*2=222 hours.  It’s slightly better than the current situation (112*2=224 hours).

5.4.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.10~11.  Under the condition of 2 engines, the minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (26 times) are slightly more than the current situation (12*2=24 times).  Under the condition of 3 engines, the minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (38 times) are slightly more than the current situation (12*3=36 times).  With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  It brings a better benefit for a company.

Table 5.10 The optimal solution of minimum worker demand for 2 engines situation with non-overlap and 8 shifts a day policy

| The minimum worker demand |  | 35 |
| --- | --- | --- |
| Assignment times |  | 26 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 8 | 4 |
| 2 | 1 | 6 |
|  | 8 | 8 |
| 3 | 1 | 10 |
|  | 8 | 12 |
| 4 | 1 | 16 |
|  | 5 | 1 |
|  | 6 | 1 |
|  | 8 | 13 |
| 5 | 1 | 13 |
|  | 8 | 11 |
| 6 | 1 | 3 |
|  | 8 | 4 |
| 7 | 1 | 4 |
|  | 8 | 4 |
| 8 | 1 | 6 |
|  | 8 | 8 |
| 9 | 1 | 10 |
|  | 8 | 14 |
| 10 | 1 | 16 |
|  | 2 | 2 |
|  | 8 | 13 |
| 11 | 1 | 13 |
|  | 8 | 5 |
| 12 | 1 | 3 |

Table 5.11 The optimal solution of minimum worker demand for 3 engines situation with non-overlap and 8 shifts a day policy

| The minimum worker demand |  | 35 |
| --- | --- | --- |
| Assignment times |  | 38 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 8 | 4 |
| 2 | 1 | 6 |
|  | 8 | 8 |
| 3 | 1 | 10 |
|  | 8 | 12 |
| 4 | 1 | 16 |
|  | 5 | 1 |
|  | 6 | 1 |
|  | 8 | 13 |
| 5 | 1 | 13 |
|  | 8 | 11 |
| 6 | 1 | 3 |
|  | 8 | 4 |
| 7 | 1 | 4 |
|  | 8 | 4 |
| 8 | 1 | 6 |
|  | 8 | 8 |
| 9 | 1 | 10 |
|  | 8 | 14 |
| 10 | 1 | 16 |
|  | 2 | 2 |
|  | 8 | 13 |
| 11 | 1 | 13 |
|  | 8 | 5 |
| 12 | 1 | 3 |
|  | 8 | 4 |
| 13 | 1 | 4 |
|  | 8 | 6 |
| 14 | 1 | 8 |
|  | 8 | 10 |
| 15 | 1 | 10 |
|  | 8 | 18 |
| 16 | 1 | 18 |
|  | 8 | 13 |
| 17 | 1 | 13 |
|  | 8 | 3 |
| 18 | 1 | 3 |

5.4.3 Summary of solutions for multi-engine situation with non-overlap and 8 shifts a day policy

Table 5.12 shows the summary of solutions in this section.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.  Under the condition of 2 engines, the last engine could be finished in 77.76*2=155.52 hours.  It’s better than the current situation (81*2=162 hours).  The minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (26 times) are slightly more than the current situation (12*2=24 times).  Under the condition of 3 engines, the last engine could be finished in 77.76*3=233.28 hours.  It’s better than the current situation (81*3=243 hours).  The minimum worker demand (35 workers) is less than the current situation (39 workers).  Assignment times (38 times) are slightly more than the current situation (36 times).

With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  It brings a better benefit for a company.

Table 5.12 Summary of solutions for the multi-engine situation with non-overlap and 8 shifts a day policy

| 2 engines |  |  |  |
| --- | --- | --- | --- |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 155.52 | 162 | 4.0 |
| Worker demand (numbers) | 35 | 39 | 10.3 |
| Assignment times (times) | 26 | 24 | -8.3 |
| 3 engines |  |  |  |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 155.52 | 162 | 4.0 |
| The time that engine 3 is done (hours) | 233.28 | 243 | 4.0 |
| Worker demand (numbers) | 35 | 39 | 10.3 |
| Assignment times (times) | 38 | 36 | -5.6 |

5.5 Solutions for multi-engine situation with overlap and 2 shifts a day policy

In this section we solve for the solutions under the condition of the multi-engine situation with overlap and 2 shifts a day policy.  Overlap for our test means an engine can start to be disassembled when the last one is processed as long as the minimum worker demand is not exceeded the current available manpower.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.

5.5.1 The earliest disassembly time for engines

Fig. 5.3~4 show the optimal solution of the multi-engine case for the earliest disassembly time under the condition of 2 engines.  The earliest disassembly time for the first engine is equal to that of the one-engine case as shown in Fig. 5.2.  As shown in Fig. 5.3, the first disassembly job for engine 1 is process (1) (starting time is 0 hour) and the latest one is process (5).  When we sum the starting time (31 hours) and the processing time (46.76 hours) of process (5), we know that engine 1 start in 0 hour and could be finished in 77.76 (31+46.76) hours.  As shown in Fig. 5.4, the first disassembly job for engine 2 is process (1) (starting time is 52 hour).  It means engine 2 can start to be disassembled when the last one is still being processed (i.e., overlap).  In current situation, the total time to disassemble an overhaul engine is 81 hours.  The time to disassemble 2 engines is 81*2=162 hours.  As shown in Fig. 5.3~4, the latest disassembly job is process (5) of engine 2.  When we sum the starting time (83 hours) and the processing time (46.76 hours) of process (5), we know that engine 2 could be finished in 129.76 (83+46.76) hours.  It’s better than the current situation (162 hours).  For the members of Clean, NDI and Bench, the work is finished in 111+80=191 hours.  It’s better than the current situation (112*2=224 hours).

Fig. 5.5 shows the optimal solution of the third engine for the earliest disassembly time under the condition of 3 engines.  The earliest disassembly time for the first and second engine is equal to that of the 2 engines case as shown in Fig. 5.3~4.  As shown in Fig. 5.4, the first disassembly job for engine 2 is process (1) (starting time is 52 hour) and the latest one is process (5).  When we sum the starting time (83 hours) and the processing time (46.76 hours) of process (5), we know that engine 2 start in 52 hour and could be finished in 129.76 (83+46.76) hours.  As shown in Fig. 5.5, the first disassembly job for engine 3 is process (1) (starting time is 104 hour).  It means engine 3 can start to be disassembled when the last one is still being processed (i.e., overlap).  In current situation, the total time to disassemble an overhaul engine is 81 hours.  The time to disassemble 3 engines is 81*3=243 hours.  As shown in Fig. 5.3~5, the latest disassembly job is process (5) of engine 3.  When we sum the starting time (135 hours) and the processing time (46.76 hours) of process (5), we know that engine 2 could be finished in 181.76 (135+46.76) hours.  It’s better than the current situation (243 hours).  For the members of Clean, NDI and Bench, the work is finished in 191+80=271 hours.  It’s better than the current situation (112*3=336 hours).

Fig. 5.3 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 1

Fig. 5.4 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 2

Fig. 5.5 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 3 engines: engine 3

5.5.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.13~14.  Under the condition of 2 engines, the minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (20 times) are less than the current situation (12*2=24 times).  Under the condition of 3 engines, the minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (27 times) are less than the current situation (12*3=36 times).

Table 5.13 The optimal solution of minimum worker demand for 2 engines situation with overlap and 2 shifts a day policy

| The minimum worker demand |  | 39 |
| --- | --- | --- |
| Assignment times |  | 20 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 2 | 4 |
| 2 | 1 | 6 |
|  | 2 | 8 |
| 3 | 1 | 10 |
|  | 2 | 12 |
| 4 | 1 | 18 |
|  | 2 | 17 |
| 5 | 1 | 17 |
|  | 2 | 15 |
| 6 | 1 | 9 |
|  | 2 | 11 |
| 7 | 1 | 10 |
|  | 2 | 12 |
| 8 | 1 | 18 |
|  | 2 | 15 |
| 9 | 1 | 13 |
|  | 2 | 5 |
| 10 | 1 | 3 |
|  | 2 | 3 |

Table 5.14 The optimal solution of minimum worker demand for 3 engines situation with overlap and 2 shifts a day policy

| The minimum worker demand |  | 39 |
| --- | --- | --- |
| Assignment times |  | 27 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 2 | 4 |
| 2 | 1 | 6 |
|  | 2 | 8 |
| 3 | 1 | 10 |
|  | 2 | 12 |
| 4 | 1 | 18 |
|  | 2 | 17 |
| 5 | 1 | 17 |
|  | 2 | 15 |
| 6 | 1 | 9 |
|  | 2 | 11 |
| 7 | 1 | 10 |
|  | 2 | 12 |
| 8 | 1 | 18 |
|  | 2 | 17 |
| 9 | 1 | 17 |
|  | 2 | 9 |
| 10 | 1 | 11 |
|  | 2 | 11 |
| 11 | 1 | 10 |
|  | 2 | 16 |
| 12 | 1 | 18 |
|  | 2 | 13 |
| 13 | 1 | 13 |
|  | 2 | 3 |
| 14 | 1 | 3 |

5.5.3 Summary of solutions for multi-engine situation with overlap and 2 shifts a day policy

Table 5.15 shows the summary of solutions in this section.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.  Under the condition of 2 engines, the last engine could be finished in 129.76 hours.  It’s better than the current situation (81*2=162 hours).  The minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (20 times) are less than the current situation (24 times).  Under the condition of 3 engines, the last engine could be finished in 181.76 hours.  It’s better than the current situation (81*3=243 hours).  The minimum worker demand (39 workers) is equal to that of the current situation (39 workers).  Assignment times (27 times) are less than the current situation (36 times).

Table 5.15 Summary of solutions for the multi-engine situation with overlap and 2 shifts a day policy

| 2 engines |  |  |  |
| --- | --- | --- | --- |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 129.76 | 162 | 19.9 |
| Worker demand (numbers) | 39 | 39 | 0.0 |
| Assignment times (times) | 20 | 24 | 16.7 |
| 3 engines |  |  |  |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 129.76 | 162 | 19.9 |
| The time that engine 3 is done (hours) | 181.76 | 243 | 25.2 |
| Worker demand (numbers) | 39 | 39 | 0.0 |
| Assignment times (times) | 27 | 36 | 25.0 |

5.6 Solutions for multi-engine situation with overlap and 8 shifts a day policy

In this section we solve for the solutions under the condition of the multi-engine situation with overlap and 8 shifts a day policy.  Overlap for our test means an engine can start to be disassembled when the last one is processed as long as the minimum worker demand is not exceeded the current available manpower.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.

5.6.1 The earliest disassembly time for engines

Fig. 5.6~7 show the optimal solution of the multi-engine case for the earliest disassembly time under the condition of 2 engines.  The earliest disassembly time for the first engine is equal to that of the one-engine case as shown in Fig. 5.2.  As shown in Fig. 5.6, the first disassembly job for engine 1 is process (1) (starting time is 0 hour) and the latest one is process (5).  When we sum the starting time (31 hours) and the processing time (46.76 hours) of process (5), we know that engine 1 start in 0 hour and could be finished in 77.76 (31+46.76) hours.  As shown in Fig. 5.7, the first disassembly job for engine 2 is process (1) (starting time is 48 hour).  It means engine 2 can start to be disassembled when the last one is still being processed (i.e., overlap).  In current situation, the total time to disassemble an overhaul engine is 81 hours.  The time to disassemble 2 engines is 81*2=162 hours.  As shown in Fig. 5.6~7, the latest disassembly job is process (5) of engine 2.  When we sum the starting time (79 hours) and the processing time (46.76 hours) of process (5), we know that engine 2 could be finished in 125.76 (79+46.76) hours.  It’s better than the current situation (162 hours).  For the members of Clean, NDI and Bench, the work is finished in 111+80=191 hours.  It’s better than the current situation (112*2=224 hours).

Fig. 5.8 shows the optimal solution of the third engine for the earliest disassembly time under the condition of 3 engines.  The earliest disassembly time for the first and second engine is equal to that of the 2 engines case as shown in Fig. 5.6~7.  As shown in Fig. 5.7, the first disassembly job for engine 2 is process (1) (starting time is 48 hour) and the latest one is process (5).  When we sum the starting time (79 hours) and the processing time (46.76 hours) of process (5), we know that engine 2 start in 48 hour and could be finished in 125.76 (79+46.76) hours.  As shown in Fig. 5.8, the first disassembly job for engine 3 is process (1) (starting time is 100 hour).  It means engine 3 can start to be disassembled when the last one is still being processed (i.e., overlap).  In current situation, the total time to disassemble an overhaul engine is 81 hours.  The time to disassemble 3 engines is 81*3=243 hours.  As shown in Fig. 5.6~8, the latest disassembly job is process (5) of engine 3.  When we sum the starting time (131 hours) and the processing time (46.76 hours) of process (5), we know that engine 3 could be finished in 177.76 (131+46.76) hours.  It’s better than the current situation (243 hours).  For the members of Clean, NDI and Bench, the work is finished in 191+80=271 hours.  It’s better than the current situation (112*3=336 hours).

Fig. 5.6 The optimal solution of the multi-engine with overlap and 8 shift a day policy the earliest disassembly time under the condition of 2 engines: engine 1

Fig. 5.7 The optimal solution of the multi-engine with overlap and 8 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 2

Fig. 5.8 The optimal solution of the multi-engine with overlap and 8 shift a day policy for the earliest disassembly time under the condition of 3 engines: engine 3

5.6.2 The minimum worker demand for system

The optimal solution of minimum worker demand is shown in Table 5.16~17.  Under the condition of 2 engines, the minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (20 times) are less than the current situation (12*2=24 times).  Under the condition of 3 engines, the minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (27 times) are less than the current situation (12*3=36 times).

Table 5.16 The optimal solution of minimum worker demand for 2 engines situation with overlap and 8 shifts a day policy

| The minimum worker demand |  | 39 |
| --- | --- | --- |
| Assignment times |  | 20 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 8 | 4 |
| 2 | 1 | 6 |
|  | 8 | 8 |
| 3 | 1 | 10 |
|  | 8 | 12 |
| 4 | 1 | 16 |
|  | 5 | 2 |
|  | 8 | 17 |
| 5 | 1 | 17 |
|  | 8 | 15 |
| 6 | 1 | 11 |
|  | 8 | 11 |
| 7 | 1 | 10 |
|  | 8 | 18 |
| 8 | 1 | 18 |
|  | 8 | 13 |
| 9 | 1 | 13 |
|  | 8 | 3 |
| 10 | 1 | 3 |

Table 5.17 The optimal solution of minimum worker demand for 3 engines situation with overlap and 8 shifts a day policy

| The minimum worker demand |  | 39 |
| --- | --- | --- |
| Assignment times |  | 27 |
| Day | Shift | Worker demand |
| 1 | 1 | 4 |
|  | 8 | 4 |
| 2 | 1 | 6 |
|  | 8 | 8 |
| 3 | 1 | 10 |
|  | 8 | 12 |
| 4 | 1 | 16 |
|  | 5 | 2 |
|  | 8 | 17 |
| 5 | 1 | 17 |
|  | 8 | 15 |
| 6 | 1 | 11 |
|  | 8 | 11 |
| 7 | 1 | 10 |
|  | 8 | 18 |
| 8 | 1 | 18 |
|  | 8 | 17 |
| 9 | 1 | 17 |
|  | 8 | 9 |
| 10 | 1 | 11 |
|  | 8 | 10 |
| 11 | 1 | 12 |
|  | 8 | 18 |
| 12 | 1 | 15 |
|  | 8 | 13 |
| 13 | 1 | 11 |
|  | 8 | 3 |
| 14 | 1 | 3 |

5.6.3 Summary of solutions for multi-engine situation with overlap and 8 shifts a day policy

Table 5.18 shows the summary of solutions in this section.  There are two conditions in this section.  One is the condition of 2 engines, the other is the condition of 3 engines.  Under the condition of 2 engines, the last engine could be finished in 125.76 hours.  It’s better than the current situation (81*2=162 hours).  The minimum worker demand (39 workers) is equal to that of the current situation.  Assignment times (20 times) are less than the current situation (24 times).  Under the condition of 3 engines, the last engine could be finished in 177.76 hours.  It’s better than the current situation (81*3=243 hours).  The minimum worker demand (39 workers) is equal to that of the current situation (39 workers).  Assignment times (27 times) are less than the current situation (36 times).

Table 5.18 Summary of solutions for the multi-engine situation with overlap and 8 shifts a day policy

| 2 engines |  |  |  |
| --- | --- | --- | --- |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 125.76 | 162 | 22.4 |
| Worker demand (numbers) | 39 | 39 | 0.0 |
| Assignment times (times) | 20 | 24 | 16.7 |
| 3 engines |  |  |  |
|  | Model solution | Current situation value | Improvement percentage |
| The time that engine 1 is done (hours) | 77.76 | 81 | 4.0 |
| The time that engine 2 is done (hours) | 125.76 | 162 | 22.4 |
| The time that engine 3 is done (hours) | 177.76 | 243 | 26.9 |
| Worker demand (numbers) | 39 | 39 | 0.0 |
| Assignment times (times) | 27 | 36 | 25.0 |

5.7 Summary of solutions for this Chapter

Table 5.19~20 show the summary of solutions in this Chapter.  First, we test our model under the condition of one-engine.  Second, we test our model under the condition of multi-engine.

Table 5.19 shows that the 8 shifts a day policy is much better than the 2 shift a day policy under the condition of one-engine.  The minimum worker demand (35 workers) for 8 shifts a day policy is less than 2 shifts a day policy (37 workers).  The assignment times (14 times) for 8 shifts a day policy are more than 2 shifts a day policy (12 times).  With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  It brings a better benefit for a company.

Table 5.20 shows that the overlap cases can speed up the finished time for engine disassembly compared with non-overlap cases.  Under the condition of non-overlap, the finished time for the last engine is slightly earlier than the current situation.  The assignment times for 8 shifts a day policy are more than 2 shifts a day policy.  With the price of the increase of assignment times, the worker demand is decreased significantly.  This is a worthy trade-off since the increase of assignment times only makes a little trouble for the engineer who is in charge of the worker assignments.  However, the decrease of worker demand reduces the cost of production a lot.  Under the condition of overlap, the finished time for the last engine is much better than the current situation.  The 8 shifts a day policy (improvement percentage is 19.9 for 2 engines) can speed up the finished time for engine disassembly compared with 2 shifts a day policy (improvement percentage is 22.4 for 2 engines).

We can suggest company A a policy in order to promote the efficiency.  Compared with the current situation, changes contain two parts.  First, overlap of the engine disassembly process with multi-engine situation defined by this research is allowed.  Second, there are eight shifts a day.  Compared with the solution shown in Table 5.21 and Fig. 5.9, the solution of modified situation as shown in Fig. 5.10 can bring much more benefit for company A.  It also can speed up the finished time for engine disassembly under the condition that the require worker demand is not exceeded the current available manpower.

Table 5.19 Summary of solutions under the condition of one-engine

|  |  |  | Model solution | Current situation value | Improvement percentage |
| --- | --- | --- | --- | --- | --- |
| The time that engine 1 is done (hours) |  |  | 77.76 | 81 | 4.0 |
| 2 shifts a day |  | Worker demand (numbers) | 37 | 39 | 5.1 |
|  |  | Assignment times (times) | 12 | 12 | 0.0 |
| 8 shifts a day | Worker demand (numbers) |  | 35 | 39 | 10.3 |
|  | Assignment times (times) |  | 14 | 12 | -16.7 |

Table 5.20 Summary of solutions under the condition of multi-engine

| 2 engines |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Model solution | Current situation value | Improvement percentage |
| The time that the last engine is done (hours) | Non-overlap | 2 shifts a day | 155.52 | 162 | 4.0 |
|  |  | 8 shifts a day | 155.52 | 162 | 4.0 |
|  | Overlap | 2 shifts a day | 129.76 | 162 | 19.9 |
|  |  | 8 shifts a day | 125.76 | 162 | 22.4 |
| Worker demand (numbers) | Non-overlap | 2 shifts a day | 37 | 39 | 5.1 |
|  |  | 8 shifts a day | 35 | 39 | 10.3 |
|  | Overlap | 2 shifts a day | 39 | 39 | 0.0 |
|  |  | 8 shifts a day | 39 | 39 | 0.0 |
| Assignment times (times) | Non-overlap | 2 shifts a day | 23 | 24 | 4.2 |
|  |  | 8 shifts a day | 26 | 24 | -8.3 |
|  | Overlap | 2 shifts a day | 20 | 24 | 16.7 |
|  |  | 8 shifts a day | 20 | 24 | 16.7 |
| 3 engines |  |  |  |  |  |
|  |  |  | Model solution | Current situation value | Improvement percentage |
| The time that the last engine is done (hours) | Non-overlap | 2 shifts a day | 233.28 | 243 | 4.0 |
|  |  | 8 shifts a day | 233.28 | 243 | 4.0 |
|  | Overlap | 2 shifts a day | 181.76 | 243 | 25.2 |
|  |  | 8 shifts a day | 177.76 | 243 | 26.9 |
| Worker demand (numbers) | Non-overlap | 2 shifts a day | 37 | 39 | 5.1 |
|  |  | 8 shifts a day | 35 | 39 | 10.3 |
|  | Overlap | 2 shifts a day | 39 | 39 | 0.0 |
|  |  | 8 shifts a day | 39 | 39 | 0.0 |
| Assignment times (times) | Non-overlap | 2 shifts a day | 35 | 36 | 2.8 |
|  |  | 8 shifts a day | 38 | 36 | -5.6 |
|  | Overlap | 2 shifts a day | 27 | 36 | 25.0 |
|  |  | 8 shifts a day | 27 | 36 | 25.0 |

Table 5.21 Summary of solutions under the condition of the 3 engines situation with non-overlap and 2 shifts a day policy (That is the current situation for company A under the condition of 3 engines)

|  | Model solution | Current situation value | Improvement percentage |
| --- | --- | --- | --- |
| The time that the last engine is done (hours) | 233.28 | 243 | 4.0 |
| Worker demand (numbers) | 37 | 39 | 5.1 |
| Assignment times (times) | 35 | 36 | 2.8 |

Fig. 5.9 Compare the optimal solution (non-overlap and 2 shifts a day) and the current situation for the multi-engine case under the condition of 3 engines

Fig. 5.10 Compare the optimal solution (overlap and 8 shifts a day) and the current situation for the multi-engine case under the condition of 3 engines

CHAPTER 6 CONCLUSIONS AND SUGGESTIONS

6.1 Conclusions

In this research, we consider the engine disassembly process which could be viewed as a job shop scheduling problem.  This problem has many real-world applications.  We develop a mixed integer programming (MIP) model for engine disassembly process.  This model contains two parts, namely, sub-model 1 and sub-model 2.  We write a DELPHI programming code to generate the constraints and variables of the model.  We solve these models using the CPLEX solver.  To illustrate the applicability of the MIP model, we present a case study on the engine disassembly process taken from an engine maintenance company (company A).

We prove that the solutions of current situation for company A not only can speed up the finish time for engine disassembly, also can minimize worker demand.  The results are satisfactory in terms of both efficiency and quality of the solution.

In addition, we suggest company A a policy in order to promote the efficiency.  Compared with the current situation, changes contain two parts.  First, overlap of the engine disassembly process with multi-engine situation defined by this research is allowed.  Second, there are eight shifts a day.  The solution of modified situation can bring much more benefit for company A.  It also can speed up the finished time for engine disassembly under the condition that the require worker demand is not exceeded the current available manpower.

6.2 Suggestions

Not all engine need to be disassembled completely.  For example, the module could be exchanged with the spare one to speed up the process.  Therefore, we may consider the un-overhaul situation.

Job shop scheduling is a NP-hard problem.  There is probably no efficient procedure for finding exactly optimal schedules.  As the computation time is important for the applicable application, we may consider developing the heuristic algorithm to improve the solutions efficiency.

Future research should concern the constraints of time interval due dates.  The objective of future study may be to develop solution procedures with the goal to minimize the total penalty cost due to earliness and tardiness of the production completion time for the engine disassembly process.

In practice, there are many examples of industrial settings in which the buffer capacity has to be taken into account.  In company A, however, the set up time of machine used is included in the processing time.  Future research could concern the impacts of the set up time.

With the variations of experience, workers have different capabilities for the same job.  Future research should consider the uncertain nature of process time.  Fuzzy theory could be used with uncertain time requirements for a job shop problem.

Nowsdays the scheduling strategy must be able to react to the need of market in a short period of time.  On the other hand, shop floor is full of exceptions; such as equipment breakdowns, tools wearing, defects occurrences, rush orders, order withdrawals, mold damages, engineering changes, manufacturing order changes, power outage, materials /personnel shortage, and ill design problems.  If shop floor scheduling cannot respond to these exceptions, prepared schedules could be inaccurate or not executable.  Therefore, the ability to handle exceptions is viable to feature research.

### Table of Contents

Abstract

中文摘要

誌謝

Table of Contents ...........…........................................................................................Ⅰ

List of Figures ..................…..................................................................................... ⅢList of Tables......................….................................................................................... Ⅳ

CHAPTER 1 INTRODUCTION	1

1.1 Research Motivations	1

1.2 Briefing of the current operation	1

1.3 Research Objectives	2

1.4 Research Scope	3

1.5 Organization	3

CHAPTER 2 LITERATURE REVIEW	4

2.1 Review of job shop scheduling problem with general form	5

2.2 Review of job shop scheduling problem with relaxed form	8

2.3 Summary	9

CHAPTER 3 REVIEW OF CURRENT STATUS	11

3.1 Engine disassembly process	11

3.2 Operation data for company A	15

3.2.1Standard disassembly process time	15

3.2.2 Definition of working hour and assignment times	16

3.2.3 Machine number and worker demand	17

CHAPTER 4 A MIXED INTEGER PROGRAMMING MODEL FOR ENGINE DISASSEMBLY PROCESS	19

4.1 A mixed integer programming formulation for sub-model 1	20

4.2 A mixed integer programming formulation for sub-model 2	24

CHAPTER 5 SOLUTIONS FOR THE ENGINE DISASSEMBLY PROCESS	27

5.1 Solutions for one-engine situation with 2 shifts a day policy	29

5.1.1 The earliest disassembly time for one-engine	29

5.1.2 The minimum worker demand for system	32

5.1.3 Summary of solutions for one-engine situation with 2 shifts a day policy	32

5.2 Solutions for one-engine situation with 8 shifts a day policy	33

Ⅰ

5.2.1 The earliest disassembly time for one-engine	34

5.2.2 The minimum worker demand for system	34

5.2.3 Summary of solutions for one-engine situation with 8 shifts a day policy	35

5.3 Solutions for multi-engine situation with non-overlap and 2 shifts a day policy	36

5.3.1 The earliest disassembly time for engines	36

5.3.2 The minimum worker demand for system	36

5.3.3 Summary of solutions for multi-engine situation with non-overlap and 2 shifts a day policy	40

5.4 Solutions for multi-engine situation with non-overlap and 8 shifts a day policy	41

5.4.1 The earliest disassembly time for engines	41

5.4.2 The minimum worker demand for system	42

5.4.3 Summary of solutions for multi-engine situation with non-overlap and 8 shifts a day policy	45

5.5 Solutions for multi-engine situation with overlap and 2 shifts a day policy	46

5.5.1 The earliest disassembly time for engines	46

5.5.2 The minimum worker demand for system	52

5.5.3 Summary of solutions for multi-engine situation with overlap and 2 shifts a day policy	55

5.6 Solutions for multi-engine situation with overlap and 8 shifts a day policy	56

5.6.1 The earliest disassembly time for engines	56

5.6.2 The minimum worker demand for system	61

5.6.3 Summary of solutions for multi-engine situation with overlap and 8 shifts a day policy	64

5.7 Summary of solutions for this Chapter	65

CHAPTER 6 CONCLUSIONS AND SUGGESTIONS	70

6.1 Conclusions	70

6.2 Suggestions	71

REFERENCES ....................…................................................……..........................73

Ⅱ

### List of Figures

Fig. 1.1 Aircraft engine	2

Fig. 3.1 The processes of the engine disassembly	13

Fig. 5.1 the description of the solutions	29

Fig. 5.2 The optimal solution of one-engine for the earliest disassembly time	31

Fig. 5.3 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 1	49

Fig. 5.4 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 2	50

Fig. 5.5 The optimal solution of the multi-engine with overlap and 2 shift a day policy for the earliest disassembly time under the condition of 3 engines: engine 3	51

Fig. 5.6 The optimal solution of the multi-engine with overlap and 8 shift a day policy the earliest disassembly time under the condition of 2 engines: engine 1	58

Fig. 5.7 The optimal solution of the multi-engine with overlap and 8 shift a day policy for the earliest disassembly time under the condition of 2 engines: engine 2	59

Fig. 5.8 The optimal solution of the multi-engine with overlap and 8 shift a day policy for the earliest disassembly time under the condition of 3 engines: engine 3	60

Fig. 5.9 Compare the optimal solution (non-overlap and 2 shifts a day) and the current situation for the multi-engine case under the condition of 3 engines	68

Fig. 5.10 Compare the optimal solution (overlap and 8 shifts a day) and the current situation for the multi-engine case under the condition of 3 engines	69

Ⅲ

### List of Tables

Table 3.1 The standard disassembly processes time defined for company A	16

Table 3.2 The working hour defined for company A	16

Table 3.3 The number of the disassembly machine and the workers demand in company A	18

Table 5.1 The six parts in Chapter 5	28

Table 5.2 The optimal solution of minimum worker demand for one-engine with 2 shifts a day policy	32

Table 5.3 Summary of solutions for the one-engine situation with 2 shifts a day policy (That is the current situation for company A under the condition of one-engine)	33

Table 5.4 The definition of 8 shifts a day policy	34

Table 5.5 The optimal solution of minimum worker demand for one-engine with 8 shifts a day policy	35

Table 5.6 Summary of solutions for the one-engine situation with 8 shifts a day policy	36

Table 5.7 The optimal solution of minimum worker demand for 2 engines situation with non-overlap and 2 shifts a day policy	38

Table 5.8 The optimal solution of minimum worker demand for 3 engines situation with non-overlap and 2 shifts a day policy	39

Table 5.9 Summary of solutions for the multi-engine situation with non-overlap and 2 shifts a day policy	41

Table 5.10 The optimal solution of minimum worker demand for 2 engines situation with non-overlap and 8 shifts a day policy	43

Table 5.11 The optimal solution of minimum worker demand for 3 engines situation with non-overlap and 8 shifts a day policy	44

Table 5.12 Summary of solutions for the multi-engine situation with non-overlap and 8 shifts a day policy	46

Table 5.13 The optimal solution of minimum worker demand for 2 engines situation with overlap and 2 shifts a day policy	53

Table 5.14 The optimal solution of minimum worker demand for 3 engines situation with overlap and 2 shifts a day policy	54

Table 5.15 Summary of solutions for the multi-engine situation with overlap and 2 shifts a day policy	55

Table 5.16 The optimal solution of minimum worker demand for 2 engines situation with overlap and 8 shifts a day policy	62

Ⅳ

Table 5.17 The optimal solution of minimum worker demand for 3 engines situation with overlap and 8 shifts a day policy	63

Table 5.18 Summary of solutions for the multi-engine situation with overlap and 8 shifts a day policy	64

Table 5.19 Summary of solutions under the condition of one-engine	66

Table 5.20 Summary of solutions under the condition of multi-engine	67

Table 5.21 Summary of solutions under the condition of the 3 engines situation with non-overlap and 2 shifts a day policy (That is the current situation for company A under the condition of 3 engines)	68

Ⅴ